## Fysik
Department of Physics and Astronomy
Please indicate the status of the activities listed by putting an X in the relevant box below (Completed, Signifiant progress, Limited progress). Please write a short comment if the priority has been replaced, further comments are optional. | [5 empty] | Leadership group discussion 16 May 2025 | Update Oct 2025
Department of Physics and Astronomy | Completed | Significant progress | Limited progress | Replaced | Comments
● Priority 1: AI4Physics |  | x |  |  | AI4Physics seminars are up and running, a specialised workshop has been co-arranged with the astroparticle group, a first learning workshop is planned. The postdoc program is not yet started. | Wait for FN decision | AI4TekNat approved by FN, funds all but postdocs
First steps that can be taken today (from 2024-2025 plans; do not change):
A),B), and D) will be implemented during 2024-25 on dept resources, including coordination. We are asking TekNat to help with the cost to primarily fund C), which will dramatically increase the impact of introducing and developing AI throughout our Section
● Priority 2: Center for Geometry and Physics: from geometry to quantum information |  |  | x |  | WINQ BUL in place. Joint QI+GCP workshop discussed. Remaining work requires new FFFs | Wait for FN decision | 3 BULs approved by FN, 2 to IFA
First steps that can be taken today (from 2024-2025 plans; do not change):
Dialogue with TekNat about the support and coordination of interdisciplinary activities between different depts. Optimizing the use of the existing external resources in the VR Excellence Center and at WINQ at Nordita. Start integrating already existing QI and quantum matter research into CGP
● Priority 3: ANItA (Academic-industrial Nuclear technology Initiative to Achieve a sustainable energy future |  |  | x |  | Adj professor from TVO Finland appointed | Consider funding opportunities from government, UUnify, excellenskluster banbrytande tekniker
First steps that can be taken today (from 2024-2025 plans; do not change): | [5 empty] | Utvärdering 2026
Broaden the current goals of ANItA and involve more programs. Ensure that the evaluation of ANItA in 2026 will be successful and the center will get prolonged support. Actively seek and identify possible candidates for hiring. |  |  |  |  | Networking with France and UK started
● Priority 4: LigHt, an environment for multi-scale characterization of (energy) materials at Ångströmlab |  | X |  |  | Ion physics merged into materials physics, reconstruction of premises completed, procurements initiated, applications to internal and external sources for funding integration, new course on hydrogen in materials, new meetings to identify and coordinate interests in LigHt and make them contribute to the development of the project, a series of joint experiments between materials physics and condensed matter physics of energy materials has been started with focus on energy materials relevant to LigHt, two postdoctoral from materials physics working part time on LigHt-related method development. | Wait for FN decision | Not funded
First steps that can be taken today (from 2024-2025 plans; do not change): | [6 empty] | Considered for infrastructure call
Merging research units, starting cross-program/departmental PhD-theses, inventory of teaching and overview of educational programs, their potential need for new advanced courses with links to the research infrastructure can be developed. PhD/Master course of materials analysis of light elements. |  |  |  |  | see also prio 3 of Material Physics and condensed matter physics of Energy Materials below. Funding for Post Doc in CPEM-programme obtained.
● Priority 5: National laboratory for instrumentation and accelerator development |  |  | x |  |  | Wait for FN decision | Not funded
First steps that can be taken today (from 2024-2025 plans; do not change): | [6 empty] | Considered for infrastructure call
Review and consolidate existing support efforts in instrumentation and infrastructure participation, identify and share key personnel, develop career plans, retain staff, replace retirements, enhance collaborations (e.g. stationing MAX IV technicians at UU) and prioritize infrastructure support. |  |  |  |  | A techer position in accelerato physics is announce by HEF program. Discussion with VR started. Discussion with universities in Sweden started.
● Priority 6: Infrastructure support |  | x |  |  |  | Ongoing as planned
First steps that can be taken today (from 2024-2025 plans; do not change):
The earlier equipment co-funding call will be reviewed and a process for co-funding needs that require fast decisions will be worked out. |  |  |  |  | The call is has been out and the applications are currently evaluated.
Research programs
Program: Applied Nuclear Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Postdoc in place; negociation with SKB progressed; market scan for DT source started | Program ony
● NESSA – NEutron Source in uppsSAla |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Next step is hiring a postdoc (should start autumn 2024). Possible installation of a weak neutron source (transferred from Lund) and facility testing with that source
Priority 2 of 3: An activity that may require department support |  |  |  |  | see Material physics | See MF
● Platform for neutron research
First steps that can be taken today (from 2024-2025 plans; do not change):
We joined the ELENA network (https://elena-neutron.iff.kfa-juelich.de) and contribute to strategies for neutron science on national and European level. Develop the NESSA neutron facility. A doctoral network (EU-GENESO) is planned. Broad support for a HiCANS as national Swedish infrastructure is established.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | Adj professor from TVO Finland is at the program since end of Jan 25; networking with France and UK started | See dept priority
● ANItA (Academic-industrial Nuclear technology Initiative to Achieve a sustainable energy future) |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Broaden the current goals of ANItA and involve more programs. Ensure that the evaluation of ANItA in 2026 will be successful and the center will get prolonged support. Actively seek and identify possible candidates for hiring.
Program: Chemical and Biomolecular Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Started: Outline new, interdisciplinary, joint research line, VR grant (N. Timneanu, PI), KAW grant (H. Ågren, co-PI). Next: Conceptualize experiments, predict (new theory), plan first studies, attract external funding. | Program ony
● Attosecond non-linear X-ray science – “New dimensions to ESCA” |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
We will start by conceptualizing experiments, predicting them with theory, planning first steps (first studies), and execute joint experiments at XFELs. We have started discussing with the European XFEL facility to have common PhD students related to attosecond non-linear X-ray science in AMO and/or chemistry.
Priority 2 of 3: An activity that may require department support |  |  |  |  | See department priority. Started in our program: CTS instrumentation grant (R. Jay), define expertise and personnel for next steps. Next steps in our program: Integrate 2 experts in national lab (salary from lab), keep knowledge/expertise in X-ray optics, X-ray instrumentation, ultrafast optical lasers, ultrafast X-rays in national lab and make knowledge available broadly. | Supported through the SNAIL umbrella
● Instrumentation development platform |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Integrate 2 of our experts in the platform (salary from the department/faculty) to keep their knowledge and expertise (in X-ray optics, X-ray instrumentation, ultrafast optical lasers, ultrafast X-rays) at the department or faculty and to make their expertise broadly available at the department, faculty, potentially nationally.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | Started: Secured external funding VR starting grant (R. Jay), VR grant (P. Wernet), WISE grant (Ph. Wernet), high-impact publications (Science, PRL, JACS, Nature Communications, Nature Chemistry), collaborations with E. Borbas (Chemistry) and S. Westenhoff (BMC), develop plans for joint PhDs with European XFEL. Next: Secure funding for and recruit up to 6 PhDs and 2 new UL/BUL, renew and grow program and TekNat hub on ultrafast X-ray spectroscopy, scattering, diffraction in physics, materials science, chemistry, catalysis and biology. | Need cross-section support to be lifted beyond program.
● Ultrafast X-rays for advanced analysis at UU (a graduate school and UL/BUL recruitments) |  |  | x |  |  | Discuss through Photon science center
First steps that can be taken today (from 2024-2025 plans; do not change):
Coordination of joint new projects within existing collaborations, submission of grant applications for ex_x0002_ternal funding: Wernet, Borbas, Ott, Lundberg, Högbohm (Stockholm University) submitted an application for a Wallenberg grant. Use the Biophysics network with their graduate students as a grad-school nucleus.
Program: Condensed Matter Physics of Energy Materials | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | We are recruiting in the areas of (i) Postdoc in Battery Research using X-ray Based Spectroscopy: Focus on advanced battery materials and their characterization using X-ray spectroscopy techniques. (ii) Postdoc in X-ray Spectroscopies for Neuromorphic Computing: Investigate materials for neuromorphic computing applications through X-ray spectroscopic methods. (iii) PhD in Experimental Studies in Quantum Technology: Conduct experimental research in the field of quantum technology, exploring new quantum materials and devices. | Program only
● Developing and implementing advanced X-ray photon science methodologies, integrating them with emerging device research |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
We are seeking candidates for positions in the field and are currently hiring researchers/postdocs associated with the new infrastructures. We are utilizing available resources to recruit PhD students who will specialize in linking X-ray and device physics in the aforementioned areas.
Priority 2 of 3: An activity that may require department support |  |  |  |  | Specifically, we consolidate in-house photoemission spectroscopy towards operando X-ray spectroscopy measurements. We have made smaller developments for operando measurements at beamlines and are heavily involved in future opportunities for spectroscopic (HAXPES) instrumentation at MAXIV, as well as time-resolved measurements at BESSY in Berlin. | Supported through the SNAIL umbrella
● Instrumentation development platform. |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Consolidating current activities involve knowledge transfer through in-house and international collaborations. We facilitate shared supervision of PhD students utilizing the infrastructures and optimize infrastructure running costs. This makes us competitive in applying for funding and beamtime already.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | We have initiated a cross-disciplinary investigation (proof of principle) demonstrating the complementarity of different families of characterization (ion and X-ray based). We are continuously developing technical designs and have started with the procurement of the different instruments. The cross-departmental project (e.g., chemistry and physics) based on these opportunities has been initiated. Funding for post doc obtained from external grant that we applied for. | Wait for FN decision
● Sustainable materials science – enabled by the LigHt infrastructure |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Merging the groups' clean energy, circular materials, and sustainable technologies research activities. Technical designs of the instrumentation and procurement of parts started. Cross-department collaborations start up their first projects. Information campaigns towards industry.
Program: High Energy Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Preparing a letter to the leadership of the department towards creating a search group for a senior lecturer. | Program only
● Accelerator-physics development towards future high-energy colliders |  |  | X
First steps that can be taken today (from 2024-2025 plans; do not change):
Alongside with the update of the European strategy for particle physics, prospect studies and infrastructure R&D must be tackled in a coherent way, not only at a global level but also within our research program, e.g. through common discussions on the future collider roadmap with the scientific staff at FREIA
Priority 2 of 3: An activity that may require department support |  |  |  |  | We brought up the idea of unit-level cross-disciplinary post-docs, waiting for feedback from the leadership. | No PDs or PhD on dept resources unless part of a larger effort/recruitment
● Inter-disciplinary post-doctoral program in high-energy physics |  |  | X
First steps that can be taken today (from 2024-2025 plans; do not change):
We request one such three-year position to be funded in order to establish a proof-of-concept also at PD level, which will formally implement joint line management across theory and experiment, to which all program members are ready to commit part of their research time.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | The activity has started and HEP has one contact person. The costing for the post-doc positions on ML has been submitted to Faculty. | Wait for FN decision
● AI4Physics |  | X
First steps that can be taken today (from 2024-2025 plans; do not change):
A), B) and D) will be implemented in 2024-2025 using department resources. We ask TekNat to help with half the cost to primarily fund C), which will dramatically increase the impact of introducing and developing AI throughout our Section.
Program: Instrumentation and Accelerators | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | The extension of the K-contract has been signed. Ordering of cryogenic components for the upgrade has started. Instrumentation for SC cavity tests at FREIA laboratory is being upgraded. Initially to be used for cavities and cryomodules from MYHRRA. Initiated collaboration efforts to participate in EU calls related to applied SC research. | Program only
● Applied superconductivity (SC) research for accelerators |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Define direction of the development of SC instruments in collaboration with industry, set milestones. Secure extension of the K-contract with CERN on the upgrade of the cryogenic test stand, set milestones.
Priority 2 of 3: An activity that may require department support |  |  |  |  | Scinetific staff from Instrum & Accel have joined discussions with the Swedish HEP community on the Swedish strategic involvement | Through HEP prio 1
● Accelerator research and development towards future particle colliders |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Integrate scientific staff with HEP community, establish joint seminars. Set up common goals and a viable strategy for the involvement of Uppsala in the international efforts towards future colliders.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | The central laser laboratory has been set up and first experiments with user groups form the department are ongoing. Discussion with materials science groups have started about joint projects at large scale facilities. | May be supported the through SNAIL umbrella
● Establish a Materials Instrumentation Platform |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
The operation of the central laser facility is currently covered by the program professor’s startup funding and external grants. Beyond 2028 1 FTE/year support will be required.
Program: Materials Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | New meeting structure with program-wide meetings to mutually inform. Lab inventory and regular follow-ups. Exchange of engineering competence with tandem laboratory. | Program only
● Structure and composition on multiple length-scales for tailored synthesis and physical properties of functional materials |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Through the ongoing merger, an inventory of experimental resources is available which is enabling the efforts towards this priority. We are currently executing the merging process, and presently explore new ways of meeting and sharing ideas
Priority 2 of 3: An activity that may require department support |  |  |  |  | Discussion with other European facilities following similar plans. Concept designs discussions. | Develop futher within program
● Platform for neutron research |  | x |  |  |  | Work through the neutron science center
First steps that can be taken today (from 2024-2025 plans; do not change):
We joined the ELENA network (https://elena-neutron.iff.kfa-juelich.de) and contribute to strategies for neutron science on national and European level. Develop the NESSA neutron facility. A doctoral network (EU-GENESO) is planned. Broad support for a HiCANS as national Swedish infrastructure is established.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | Instrument procurement initiated. New activities in hydrogen-related research together with inorganic chemistry. New meeting structure in program. Department priority in ÖB. | Wait for FN decision | Not funded
● A science platform for studying hydrogen in materials |  | x |  |  |  | Work to identify BUL candidate to submit VR BUL application? | Considered for infrastructure call
First steps that can be taken today (from 2024-2025 plans; do not change): | [5 empty] | Dept infrastructure support already decided
Merging the two groups and consolidating H-related science activities. Technical designs of instrumentation. Identifying science cases within the faculty suitable to be addressed. Make an inventory of hydrogen related teaching activities at the faculty; start developing further. Information campaigns towards industry. | [5 empty] | Effort for more coherent communcation outwards, beyond dept.
Program: Nuclear Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Completed: The Belle II authorship of the group, and the GNN paper that is very close to submission. In addition, the GNN project has been extended thanks to a guest PhD student which is expected to yield another publication. Our group has been invited to the EU project JENNIFER3 in which we will explore machine learning methods for Belle II data analysis. In progress: Due to 2*parental leave, the Dalitz decay study has a short pause but will be resumed in March. The charm polarization study is in progress; the group has given several presentations at Belle II working group meetings and collaboration meetings. | Program only
● Femtoscale investigations of matter and antimatter with Belle II and PANDA |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
A paper draft should emerge from our hyperon Dalitz decay study with PANDA@HADES within a year and one from the Geometric Deep Learning project. Our Belle II entry contribution tasks should be completed for full authorship. A memo for internal Belle II review should emerge from the charm polarization project.
Priority 2 of 3: An activity that may require department support |  |  |  |  | In progress: 50% of a senior position is allocated to the continued assembly of the pellet tracking system. We have applied for infrastructure funding from IFA to build a frozen CO2 target with detector modules, and will apply for further funding from Carl Trygger. We are in close contact with cluster jet developers in Muenster. | Fits within the SNAIL umbrella
● Targeting a new era of hyperon physics with deep learning |  | x |  |  |  | Handled through dept infrastructure fund calls
First steps that can be taken today (from 2024-2025 plans; do not change):
The assembly of the pellet tracking system as well as knowledge transfer is currently ongoing. We applied for external funding to increase the committed person power. Furthermore, we are already establishing the necessary international networks in which these activities will be driven.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | In progress: LHCb analysis in progress on semileptopnic baryon decays. The XiXibar analysis, carried out in collaboration with Warszaw and IHEP, with the full BESIII data sample is in an advanced state. NNBAR: Ageing tests of crystals show promising results, the next step is to validate MC using cosmic muon data, and to test a new readout system. Theory: Paper drafts exist of 1. calculations of non-leptonic baryon decays to test CP violation. 2. Prospects for rare semi-leptonic baryon decays with the CBM experiment. 3. Chiral structure of baryons.
● High-Precision Searches for the Mechanisms of Baryogenesis in the Early Universe (with BESIII, LHCb, ESS and theory) |  | x |  |  |  | No PDs or PhD on dept resources unless part of a larger effort/recruitment
First steps that can be taken today (from 2024-2025 plans; do not change):
BESIII and LHCb: analyses of data that are already on tape (Adlarson, Eklund, Kupsc, IFA postdoc and PhDs); NNBAR: assess suitability of WASA detector (Eklund, Kupsc, Marciniewski, Wolke); theory: calculations of weak processes with master students and/or external collaborators (Kupsc, Leupold).
Program: Observational Astrophysics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Program staff had two strategy discussion meetings with a number specific conclusions related to future recruitment, redistribution of tasks in the infrastructure development projects, as well is teaching. | Program ony
● Recruitment of BUL/UL to strengthen the program's research areas |  | x |  |  |  | Expert group report
First steps that can be taken today (from 2024-2025 plans; do not change):
Internal discussion of staff interests and future plans. Discussions with the Theory program and new recruits about changes that we expect/would like to see. Discussions with the advisory group established for the PaP replacement.
Priority 2 of 3: An activity that may require department support |  |  |  |  | The ELT ANDES project is successfully going through Preliminary Design Review. Of the two WPs with leadership and responsibility in UU one (software) has already passed the PDR and the fiber optics is going through it on February 24th. MOSAIC consortium finally decided that Sweden will produce the data reduction pipeline. | Expert group report and progress with new BUL recruitment
● Recruitment of UL/Professor to lead instrumentation development projects. |  | x |  |  |  | Infrastructure support decided
First steps that can be taken today (from 2024-2025 plans; do not change):
Setting up an external advisory group for recruitment (in progress). Compiling specifications and assessing optical design for the fiber link of ANDES (in progress). Preparing call for tender for the fiber optics slit unit (end of 2024). Formulating the requirements for the new recruitment and starting a search group (2025).
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | A number of internal discussions within the program and between programs in the Division. | Wait for FN decision | AI4TekNat approved by FN, funds all but postdocs
● Cross-disciplinary center for AI and ML specialized on physics and astronomy |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Identification of interest from IFA programs and identification of people interested in contributing to the Center.
Program: Physics Education Research | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | The last application from VR was not granted any money. New efforts are being done and we hope for better success this year. | Program only
● Re-establishing the PER program via external money |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
The PAP has initiated the application process by attending meetings arranged by the research support unit, to be able to tailor the best possible application. Meanwhile, the PAP has also applied for project money for the SCALE project, that will allow the program to focus on increasing the research output and visibility.
Priority 2 of 3: An activity that may require department support |  |  |  |  | See comments from the department level. Also, we have published much on the eduacational aspects of AI and aslo developed a course for the department that addresses the use of AI in research and education. | AI4Physics | AI4TekNat approved by FN, funds all but postdocs
● AI4Physics |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
A),B), and D) will be implemented during 2024-25 on dept resources. We are asking TekNat to help with half the cost to primarily fund C), which dramatically increase the impact of introducing and developing AI throughout our Section
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | We need to contiunue our efforts to get more FFF to be able to maintain the reseaehc quality and international reputation we have, since more and more of our resources are being used for other duties within the department (such as developing teching, AI and directorship for UG). | Work on Prio 1 on increasing external support first
● Re-establishing the PER program |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
See Prio 1 above. Meanwhile, the PAP has also applied for project money from VR for the SCALE project and other projects , that will allow the program to focus on increasing the research output and visibility. These efforts will continue in the near future to maintain the research by the program.
Program: Quantum Matter Theory (QMT) | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Offer made 5 Feb 2025. If accepting, completed prio. | Program only | Done
● New UL recruitment |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
We have had already a national search group (members from KTH and Lund) helping with formulating the details of the position and call. We are currently finalizing the announcement. We will directly reach out to identified interesting candidates to inform them about the open position.
Priority 2 of 3: An activity that may require department support |  |  |  |  | Department working group will be formed. | Same as MT, TF
● More uniform research salary support for faculty members |  |  | x |  |  | Form working group with the unit leaders. Lars sammankallande.
First steps that can be taken today (from 2024-2025 plans; do not change):
Determining the level of uniform faculty research that would be possible and then analyzing the changes needed within the department. Identifying the best way to administratively handle the new arrangement, possibly with the department centrally paying salaries. Finding a way of handling the transition.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | Prio joined with TP and Math into joint prio. Nordita BUL already active at UU. Teaching with IT dept scheduled for HT26 | Wait for FN decision | 3 BUL approved by FN. 1 to QMT.
● Quantum Information (QI) |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Maximize the possibilities the new Nordita BUL is giving by incorporating the Nordita QI staff into UU activities. Work on association with WAQCT through Nordita. Expanding interactions with the IT department before formal structure is in place.
Program: Space and Plasma Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | We are preparing an announcement for a PhD position with start in fall 2025. | Program only
● Planetary and cometary PhD
First steps that can be taken today (from 2024-2025 plans; do not change):
The first step is to identify a short list of possible projects which can be used as a base for the PhD project, and also can be used in applications for external funding in the coming years.
Priority 2 of 3: An activity that may require department support |  |  |  |  | This priority is lifted up to the department level. | AI4Physics | AI4TekNat approved by FN, funds all but postdocs
● AI4Physics
First steps that can be taken today (from 2024-2025 plans; do not change):
A), B), and D) will be implemented during 2024-25 on the IFA level. At the program level we already plan several AI-related activities during 2024-25. We are procuring server equipped with several GPUs to be used for AI-related computations. We included AI-related projects in some of the funding applications in 2024.
Priority 3 of 3: An activity that may require faculty support | [5 empty] | Work through division.
● URAC: Uppsala Rymd- och AstrofysikCentrum
First steps that can be taken today (from 2024-2025 plans; do not change):
PAP and PhD student will attend workshop at ISSI (Bern) on Electron Astrophysics 2024. Previous PAP will participate in a national workshop on stellar winds from evolved stars 2024. Emphasize astrophysical applications in ongoing and proposed space plasma projects.
Program: Theoretical Astrophysics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Seminar by Sarin attracted large audience across divisions (High energy, Nuclear, Astro). Christian Glaser from High-Energy Physics brought in as co-supervisor of PhD student in Theoretical Astro. Joint Masters project between Astro (Korn) and High-Energy Physics (O'Sullivan). Gravitational wave component added to Theoretical Astrophysics course given in HT24. | Program only
● Exploring possible synergies in Multi-Messenger Astrophysics |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
We have a first joint seminar booked in for May 2024, Nikhil Sarin from Nordita. We aim for at least one such seminar per semester.
Priority 2 of 3: An activity that may require department support |  |  |  |  | The activity has started and Astro has one contact person. Prio. lifted by department, and the costing for the post-doc positions has been submitted to the Faculty. | Wait for FN decision | AI4TekNat approved by FN, funds all but postdocs
● AI4Physics |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
A), B), and D) will be implemented during 2024-25 on dept resources. We are asking TekNat to help with half the cost to primarily fund C), which dramatically increase the impact. TAP already has activity in this direction in the 4MOST project with an eSSENCE PhD student.
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | Prio. was strongly supported by the KoF panel. Two PhD students will be hired in the program this spring as planned. | Wait for TN being integrated into activity.
● Strengthening Stellar Astrophysics |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Concrete discussions regarding timing and directions for a possible faculty position, both within the program and in the division. Strengthening of the PhD student cohort in this activity will also take place via hiring of PhD students during spring next year
Program: Theoretical Physics | Completed | Significant progress | Limited progress | Replaced | Comments
Priority 1 of 3: An activity that can be accomplished within the program |  |  |  |  | Joint work wit the department to resolve the issue | Program only
● Survival of Theoretical Physics program |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
We are in dialog with the department about budget optimization. Furthermore, we request all faculty within the program to apply for grants which may cover some fraction of their salary.
Priority 2 of 3: An activity that may require department support |  |  |  |  | The department will form the working group looking into these issues. | Same as MT, QMT
● More uniform research salary support for faculty members |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Determining the level of uniform faculty research that would be possible and then analyzing the changes needed within the department. Identifying the best way to administratively handle the new arrangement, possibly with the department centrally paying salaries. Finding a way of handling the transition
Priority 3 of 3: An activity that may require faculty support |  |  |  |  | This priority is lifted up to the department level and it has been merged with another priority from the Quantum Material Physics. | Same as QMT
● Centre for Geometry and Physics |  |  | x
First steps that can be taken today (from 2024-2025 plans; do not change):
Dialogue with the Faculty about the joint positions in geometry and physics between the Departments of physics and Astronomy and Mathematics in order to create a proper framework, beyond informal agreements between department chairs. Dialogue with the Faculty about the support of the
MISSING!
Program: Materials Theory
Prio 1: Securing excellence in light of retirements | [5 empty] | Program only
Prio 2: More uniform research salary support for faculty members | [5 empty] | Same as QMT, TF
Prio 3: Securing excellence in light of retirements | [5 empty] | Wait for WISE recruitment | Expert group. Consider KAW Professor recruitment