## Slide 1: The FREIA Test Program
Roger Ruber
for the Uppsala Accelerator Group & FREIA
20-21 November 2013, Uppsala
ESS-FREIA Spoke Cavity Testing Review and Planning Meeting

## Slide 2: Responsibility for ESS Accelerator
Contribution to the technical design & construction effort
  design concept spoke accelerating cavity power source
  design concept radio-frequency (RF) power distribution
  survey test stand infrastructure and requirements
  study of upgrade scenarios RF systems for ESS power upgrade
Development power station for spoke cavities
  soak test with water cooled load, then accelerating cavity, incl. controls
  collaboration with industry to develop vacuum tube and solid-state based prototypes
System test, power station with spoke cavity and cryostat-module
  fully dressed prototype cavity (in test cryostat)
  complete prototype module (2 spoke cavities)
Acceptance test cryostat-modules (proposal submitted)
  for all final modules before installation

## Slide 3: What (does this mean)?
Criteria to judge the test results
Efficiency
  to reduce electricity costs
  reuse cooling water
Stability
  relative fast response to perturbations
  predictability of the system
  requires testing of extreme conditions
Reliability
  slow variations such as drift and aging that affect parameters
  abrupt failure of something
  requires long-term soak testing

## Slide 4: … for the sub-systems …
RF power station & RF distribution
  achieve required performance: 14 Hz, 2.9+tfill ms, power-to-beam+overhead kWpeak
  stable long term operation
  safe handling of reflections, sparking, interlocks and faults
LLRF and controls
  RF control (1% amplitude, 1o phase)
  compensation Lorentz detuning & microphonics
Spoke cavity
  achieve required performance: Eacc, Q0, f0, losses
  stable long term operation
Spoke cryo-module
  as for single cavity
  no undesirable coupling between cavities
  achieve cryogenic requirements: cool down, losses

## Slide 5: How ?
General idea
  commission and test infrastructure before arrival sub-systems
    new facility, so must commission equipment to guarantee proper operation
    personnel should have time to familiarize with equipment
  commission and test each equipment before combining
    limited time line towards arrival of cavity
    limited learning curve towards prototype cryo-module testing
Will be first major test for FREIA & ESS (of a whole accelerator section)
  critical for decision towards cavity series production
  critical for decision towards RF & LLRF component design and procurement
2013 | 2014 |  |  |  |  |  |  |  |  | 2015 |  |  | 
December | Jan | Feb | Mar | Apr | May | Jun |  |  |  |  | June |  | Dec.
Helium Liquefier
RF Power Station
Spoke Cavity
LLRF
HNOSS Horizontal Cryostat
2K pumps
Cryo-module
today

## Slide 6: Cryogenics & Cryostat
Helium and Nitrogen Cryogenics: contract with Linde
  factory test (cold box & controls): January
  delivery & installation: February-March
  commissioning & acceptance test (by Linde): March-April
HNOSS Cryostat and Transfer Lines: contracts with ACS and Cryo Diffusion
  factory test (LN2): April
  delivery & installation: May-June
  commissioning (by UU and ACS): Summer
Sub-atmospheric pumps: tender launched last week
  delivery & installation: May-June
  commissioning: Summer
2013 | 2014 |  |  |  |  |  |  |  | 
December | Jan | Feb | Mar | Apr | May | June | July |  | 
Helium Liquefier
HNOSS Horizontal Cryostat
2K pumps
today

## Slide 7: RF Power Station and Distribution
Tetrode based: contract with Electrosys
  factory test tetrodes (Thales, Thonon): this week
  factory test (Electrosys):
  delivery & installation: January-February
  commissioning and acceptance test (by Electrosys): February-March
Solid-state based:Siemens development
  on loan to Uppsala, expected delivery: February
RF Distrbution
  circulator and loads ordered
  tender of remaining parts now under preparation
2013 | 2014 |  |  |  |  |  |  |  | 
December | Jan | Feb | Mar | Apr | May | June | July |  | 
Tetrode
Solid State
today

## Slide 8: Controls and Monitoring
Safety
  radiation monitoring
  personnel & equipment safety interlocks
Equipment controls
  base controls included in contracts (Cryo Diffusion, Electrosys, Linde)
  overall integration by Uppsala (EPICS based), working with equipment manufacturers
Data acquisition and monitoring
  RF measurements (amplitude, phase)
  infrastructure & environment monitoring (temperature, pressure & humidity)
  … any special experiments …
LLRF
  under development at Lund, updated as testing progresses…
2013 | 2014 |  |  |  |  |  |  |  | 
December | Jan | Feb | Mar | Apr | May | June | July |  | 
LLRF
today

## Slide 9: Single “Double Spoke” Cavity
Only after all other systems have been successfully commissioned
Then…
install cavity into cryostat
  tooling under design by ACS
connect cavity vacuum pumping
  always keep pumping if possible…
connect to cryogenics, RF etc.
connection & functionality test
  RF couplers, tuners and instrumentation
  Note that this will be the first time
  (for cavity, cryostat and team)
  Expect extra time for
  connections
  cool down, RF conditioning, testing…

## Slide 10: Spoke Cryo-module
We have one year to test the first spoke cavity
should make optimum use to do it careful
exhaustive testing for efficiency, stability and reliability
do it carefully and learn how to operate equipment and assembly
polish any issues
  to prepare for order of series production
  arrival of prototype cryo-module
Prototype spoke cryo-module
repeat the single cavity experience
test cryostat behaviour
search for any correlation and interactions between cavities
polish any issues and learn to install/test/remove
  prepare for series testing of cryo-modules

## Slide 11: Summary
Further discussions during this meeting
  We have ideas on the testing but want to discuss with you for your input and experience
  Onset to a commonly agreed test program
Thanks to you all !
http://blog.qatestlab.com/2011/04/01/how-to-involve-non-functional-testing-in-your-project/