## Slide 1: Vertical Cryostat Kick-off metting
Control System Presentation

## Slide 2: Schedule
Control system definition
Project organization presentation
The benefit of our passed experience

## Slide 3: Control System Hardware definition
One Siemens PLC architecture
  1 CPU S7-315-2PN/DP
  5 extension rack for I/O interface cards
Cernox, Edwards, MKS, AMI modules
Integrated into a single cabinet:
  3600 Total length
  1200 glass doors
  1 socle of 200 height
Including adapted power departures

## Slide 4: Control System Hardware definition
1 computer (Dell Optiplex) with 1 screen
1 Siemens WinCC software licence embedded
All connection between the cabinet and the Cryostat
Ethernet connection are not included

## Slide 5: Control System Application definition
1 PLC program including
  all the sequence definition
  Communication with the specific equipement
1 Scada application allowing
  the control of all the sequence
  The alarms and default display
  The archive of data to display trends
Existing template used
  Standard
  Information available for Epics

## Slide 6: Project organization
Team organization
  IsiiTech
    1 Administrative responsible
    1 Project manager
    1 PLC programmer
    1 Scada programmer
  Electrical partner
    1 Electrical installation manager in charge of conception of the cabinet and the cabling
    1 Electrical schema designer
    1 Electrician team
d

## Slide 7: Project Steps
Process studies
  P&ID validation
  All the sequence definition
  Input / Output definition list
Hardware Studies
  To define PLC architecture
  To define the cabinet plan
  Taking in charge the connectors definition
  To optimize the cabling into the cabinet

## Slide 8: Project Steps
Studies validation
PLC Hardware architecture realization
Cabinet construction
PLC Programming
Scada programming
Programs test
  In our office
  Without the equipment (sequence, manual mode,…)

## Slide 9: Project Steps
Cabinet reception at electrician workshop
Cabinet delivery at CD workshop
Cabinet – Cryostat connection
  Definitive connection into the cabinet
  Spare length at the bottom of the cabinet
Cryostat sequence tests at CD workshop
    Up to 4 weeks to test and adjust the program

## Slide 10: Project Steps
Disconnection
  On the equipment side (Connectors)
Cabinet installation on site (done by CD)
Cable installation and Connection
Electrical test & unit test: 1 week
Sequence test: 4 noncontiguous weeks on site
1 operating manual redaction

## Slide 11: The benefits of our experience
Connectors optimization
Specific equipement knowledge
Equipment operation

## Slide 12: Warning
Multiple Insert: to study
?

## Slide 13
Thank you !