## Slide 1: Uppsala University Contract UH2015/09 - UA2016/05 Job nr. 5973
Vertical Cryostat GERSEMI
1rst follow-up meeting
21/06/2016

## Slide 2
JOB STATUS
WP1: double re-heater
  Planned status: manufacturing design 100%
  Actual status: manufacturing design 90%
    Delivery target remains in November 2016
    Manufacturing drawings to be send to ACS this week (W25) for approval W26

## Slide 3
JOB STATUS
WP2: cryostat
  Planned status: manufacturing design 50%
  Actual status: manufacturing design 0%
    Main planning risk
    Studies to be started after design input is 100% sure (see magnet workshop presentation)
    Planning risk mitigation with large flange semi-finished products order on week 27 (initially planned after design studies)

## Slide 4
JOB STATUS
WP3: magnet insert
  Planned status: manufacturing design 0%
  Actual status: manufacturing design 0%
WP4: bath insert
  Planned status: manufacturing design 0%
  Actual status: manufacturing design 0%

## Slide 5
JOB STATUS
WP5: valves box
  Planned status: manufacturing design 100%
  Actual status: manufacturing design 0%
    Main planning risk
    Studies to be started after design input is 100% sure (see magnet workshop presentation)
    Planning risk mitigation with large flange semi-finished products order on week 27 (initially planned after design studies)

## Slide 6
JOB STATUS
WP6: transfer lines
  Planned status: manufacturing design 0%
  Actual status: manufacturing design 0%

## Slide 7
JOB STATUS
Subcontracting
  Control system: order agreement on 13/06
  Vacuum containement: 3D preliminary models presented on 03/06 ; order planned on W27
HNOSS after-sales
  Interconnexion box and transfer line received on 16/06
  Control system: MKS controller given today to ISII-Tech

## Slide 8
Detailed planning & milstones
WP1: double re-heater
  Manufacturing drawings acceptance: W26
  Procurement: W26->W36
  Manufacturing&Tests: W36->W42
  Final test (LT): W42
  Delivery: W45

## Slide 9
Detailed planning & milstones
WP2: cryostat
  Design inputs: W26
  Review with ACS: W27
  Manufacturing design review: W40
  Procurement: W27->W01/17
  Manufacturing: W01/17->W16/17
  Intermediate tests:
    Pressure vessel parts RT/VT/dim W06/17
    Pressure vessel assembly RT/VT/dim W09/17
    Pressure vessel pressure and leak test W11/17

## Slide 10
Detailed planning & milstones
WP3: magnet insert
  To be planned
WP4: bath insert
  To be planned

## Slide 11
Detailed planning & milstones
WP5: valves box
  Design inputs: W26
  Review with ACS: W27
  Manufacturing design review: W36
  Procurement: W27->W42
  Manufacturing: W42->W52
  Intermediate tests:
    4K pot test W44
    HX leak tests W46
    Valves box final tests (LN2, LT) W50->W52

## Slide 12
Detailed planning & milstones
WP6: transfer lines
  To be planned
Assembly, calbling and tests: W21 ->W25