## Slide 1: Uppsala University Contract UH2015/09 - UA2016/05 Job nr. 5973
Vertical Cryostat GERSEMI
2nd follow-up meeting
25/10/2016

## Slide 2
JOB STATUS
WP1: double re-heater
  Planned status:
    To termination 80%
    Initially planned task: manufacturing 50%
  Actual status:
    To termination 65%
    Actual task: manufacturing 25%
    On critical path: external vessel delivery on W47
    Delivery target W50

## Slide 3
JOB STATUS
WP2: cryostat
  Planned status:
    To termination: 44%
    Initially planned task: Vacuum vessel procurement 80%
  Actual status:
    To termination: 36%
    Actual tasks:
      Vacuum vessel procurement 75%
      Manufacturing drawings 50%
    On critical path: Vacuum vessel procurement
    Manufacturing start date: W1/2017
    Manufacturing end date: W20/2017

## Slide 4
JOB STATUS
WP2: cryostat
  Vacuum vessel: ready to be manufactured at SOMINEX
  Lambda Plate: will be machined and finished at EFINOR
  Dewar: Manufacturing dimension submitted by CD to ACS for validation

## Slide 5
JOB STATUS
WP3: magnet insert
  Planned status:
    To termination: 33%
    Initially planned task: manufacturing procedures: 100%
  Actual status:
    Design to be given by CERN
    Deadline for design: S49/2016
WP4: bath insert
  Planned status:
    Finished
  Actual status:
    Manufacturing design completed
    Manufacturing end date: W03/2017

## Slide 6
JOB STATUS
WP3: magnet insert
  Inputs to be given by CERN (required power)
WP4: bath insert
  Burndy connector implemented
  Level sensor in two parts
  Insulation in Klegecell
  Safety valve design

## Slide 7
JOB STATUS
WP5: valves box
  Planned status:
    To termination: 80%
    Initially planned task:
      Procurement 80%
      Manufacturing 10%
  Actual status:
    To termination: 45%
    Actual tasks:
      Manufacturing drawings 50%
      Procurement 80%
    On critical path: Manufacturing drawings
    Manufacturing start date: W1/2017
    Manufacturing end date: W8/2017

## Slide 8
JOB STATUS
WP5: valves box
  Control valves by WEKA: ready to be delivered
  Stop valves by VELAN (extra KV): in manufacturing
  Stop valves by SELFA (low KV): in manufacturing
  Heat exchanger by DATE: in manufacturing
  Vacuum vessel by SOMINEX: manufacturing drawings in review by ACS

## Slide 9
JOB STATUS
WP6: transfer lines
  Planned status: manufacturing design 0%
  Actual status: manufacturing design 0%
  Start date: W49/2016

## Slide 10
JOB STATUS
Subcontracting
  Control system:
    Start date November 2016
  Vacuum containment:
    Delivery date @ Cryodiffusion December 2016
  Cabling (internal + feedthrough)
    January 2017 (CD needs Cernox sensor calibrated)
HNOSS after-sales
  ICB:
    Leak detected on LN2 circuit, only during cooldown
    Supposed on Al/SS transition on lower thermal screen
  Transfer line received:
    No leak detected
    1x DN40KF port added
  Control system:
    MKS controller and valve tested by ISII-Tech
    VAT solution found
    Problem on MKS valve detected by ISII-Tech and investigated by CD: closed limit swith failed.

## Slide 11
JOB STATUS
Procurement:
  Cryogenic valves to be delivered December 2016
  Cryogenic HX to be delivered December 2016
  Cernox sensors (?)
  Other material defined and reviewed by ACS on W40/2016: final list to be released

## Slide 12
JOB STATUS
Procurement:
  Other material:
    Butterfly control valves: VAT
    Vacuum valves: VAT
    Pressure sensors: BROOKS
    Vacuum sensors: Pfeiffer (model to be confirmed)
    Temperature sensors: Cernox
    Flowmeters: BROOKS
    Film heaters: Winkler (test to be done by ACS)
    Gas heaters: Vulcanic with helical finned copper tube
    Level sensors: AMI
    Cryogenic valves
      WEKA: Control Valves
      VELAN: High KV stop valves
      SELFA: Low Kv stop valves