Romeo cavity test with power coupler: planning

19 January 2017

07:10

Planning

- this week

  - finish installation ICB and transfer lines

  - test transfer lines and HNOSS

  - install instrumentation and MLI on Romeo cavity

  - verify connection interface between HNOSS and cavity input coupler

  - verify connections cavity input coupler (instrumentation, RF)

- next week starting 23 January

  - finish preparations

  - test procedure to roll Romeo cavity into HNOSS

  - connect and test instrumentation on cavity when inside HNOSS

- week starting 30 January

  - [Mon/Wed 30-Jan/01-Feb]

    - final installation Romeo in HNOSS

    - final connections vacuum, cold tuner

    - test vacuum, cold tuner, instrumentation

  - [Thu/Fri 02/03-Feb]

    - final connections input coupler

    - connect RF waveguide to input coupler

- week starting 6 February

  - start vacuum pumping Romeo cavity

  - close HNOSS

  - start vacuum pumping HNOSS

  - RF re-conditioning input coupler at warm

- week starting 13 February

  - cool down HNOSS and Romeo

  - stabilize at 2K

  - RF re-conditioning input coupler with cavity detuned

  - start other testing and verifications