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Planning
· this week
· finish installation ICB and transfer lines
· test transfer lines and HNOSS
· install instrumentation and MLI on Romeo cavity
· verify connection interface between HNOSS and cavity input coupler
· verify connections cavity input coupler (instrumentation, RF)
· next week starting 23 January
· finish preparations
· test procedure to roll Romeo cavity into HNOSS
· connect and test instrumentation on cavity when inside HNOSS
· week starting 30 January
· [Mon/Wed 30-Jan/01-Feb]
· final installation Romeo in HNOSS
· final connections vacuum, cold tuner
· test vacuum, cold tuner, instrumentation
· [Thu/Fri 02/03-Feb]
· final connections input coupler
· connect RF waveguide to input coupler
· week starting 6 February
· start vacuum pumping Romeo cavity
· close HNOSS
· start vacuum pumping HNOSS
· RF re-conditioning input coupler at warm
· week starting 13 February
· cool down HNOSS and Romeo
· stabilize at 2K
· RF re-conditioning input coupler with cavity detuned
· start other testing and verifications
