## Front Page
FREIA Laboratory
Dept. of Physics and Astronomy
Uppsala University
Document No.: |  | Experiment Document No.: |  | Created: |  | 2017-01-27 | Page: | 1
|  |  |  | Modified: |  | 2017-01-28 | Rev. No.: | 1.1
Engineering Specification
ESS Dressed Spoke Cavity Test
| Prepared by |  | Checked by |  |  |  | Approved by
H.Li
V. Goryashko
R.J.M.Y. Ruber
Distribution List

## Procedure
ESS Dressed Spoke Cavity Test
Step | Process or Check Item | Overall Time [days] | In Bunker [days] | Team | Sub-step | Work Description | Acceptance Criteria | Check Sheet | Parts | Tools and Instruments | Utilities and Services
Week starting 9 January
1 | Shipment from Orsay to Uppsala | 2 | [8 empty] | mobile crane, fork lift
2 | Arrival, unloading | [9 empty] | mobile crane, fork lift
3 | Unpacking |  |  |  | a | opening box
[5 empty] | b | read-out shock data logger
Week starting 16 January
4 | Inspection |  |  |  | a | external inspection | no visual damage
[5 empty] | b | mechanical parts
[5 empty] | c | instrumentation connections | electrical |  |  | multimeter, test box
[5 empty] | e | cold tuner verification | piezo and stepper motor
5 | Instrumentation |  |  |  | a | temperature sensors
[5 empty] | b | heaters
Week starting 23 January
6 | Test insertion | 2 |  |  | a | put cavity on the insertion tooling
[5 empty] | b | roll cavity inside HNOSS
[5 empty] | c | verify final position
[5 empty] | d | verify vacuum connection
[5 empty] | e | verify cryogenic connections
7 | Instrumentation | 1 |  |  | a | connect cavity instrumentation to HNOSS
[5 empty] | b | verify instrumentation
8 | Remove cavity from HNOSS | 0.5 |  |  |  | roll cavity out from HNOSS
9 | Instrumentation | 0.5 |  |  |  | install remaining two temperature sensors
10 | MLI | 1 |  |  |  | install MLI
Week starting 30 January
11 | Re-arrange insertion tool | 0.5 |  |  | a | lift cavity from insertion tooling
[5 empty] | b | re-arrange insertion tooling
[5 empty] | c | put cavity back on the insertion tooling
12 | Insertion | 1 |  |  | a | roll cavity inside HNOSS |  |  |  | insertion tool
[5 empty] | b | lower cavity to final position
[5 empty] | c | attach cavity to tie rods |  |  |  | tie rods
[5 empty] | d | adjust cavity position | level, rotation
13 | Bellows | 1 |  |  | a | installation bellows for power coupler
[5 empty] | b | final adjustment cavity position | level, rotation
14 | Cavity connection | 1 |  |  | a | connect cavity cryogenic lines
[5 empty] | b | connect cavity vacuum line
[5 empty] | c | connect instrumentation
[5 empty] | d | connect cold tuner system
15 | Leak test | 0.5 |  |  | a | vacuum line
[5 empty] | b | cryogenics line
16 | Vacuum |  |  |  |  | start cavity vacuum pumps
17 | Instrumentation | 0.5 |  |  | a | instrumentation check |  |  |  | multimeter, test box
[5 empty] | b | cold tuner check
18 | Power coupler installation | 1 |  |  | a | install antenna |  |  |  | IPNO tooling
[5 empty] | b | install door knob
Week starting 6 February
19 | Power coupler connection |  |  |  | a | connect cooling water
[5 empty] | b | connect SHe cooling
[5 empty] | c | connect instrumentation
20 | Power coupler instrumentation |  |  |  |  | instrumentation check |  |  |  | multimeter, test box
21 | RF distribution |  |  |  |  | final connection waveguides
22 | Closure HNOSS |  |  |  | a | close thermal shield
[5 empty] | b | close flanges
[5 empty] | c | close main doors
23 | Leak test |  |  |  |  | vacuum leak test HNOSS
24 | Vacuum |  |  |  |  | start HNOSS vacuum pumps
25 | Close bunker |  |  |  |  | close main bunker gate
26 | Measurement |  |  |  | a | S parameter measurement | Qext |  |  | VNA
[5 empty] | b | tuning range of the slow step tuner at warm temperature |  |  |  | Labview, VNA
27 | RF |  |  |  |  | conditioning coupler | reach full power, pulse length |  |  |  | RF source
28 | Measurement |  |  |  |  | cavity frequncy checking |  |  |  | VNA, Labview
Week starting 13 February
29 | Cool down | 1 |  | CRYO | a | cool down with LN2 of transfer line and thermal shield |  |  |  |  | LN2
|  | 2 |  |  | b | cool down to 4 K |  |  |  |  | Liquefier
|  | 1 |  |  | c | stabilize at 4 K
|  | 1 |  |  | d | cool down to 2 K |  |  |  |  | 2K pumps
[5 empty] | e | cooling coupler |  |  |  |  | SHe pumps
Week starting 13 February
30 | Measurement | 1 |  |  |  | sensitivity to helium pressure fluctuation |  |  |  | VNA, Labview
31 | CTS Calibration | 0.5 |  |  |  | tuning range of the slow step tuner at cold temperature |  |  |  | Labview, SEL, frequency meter
32 | RF Calibration | 0.5 |  | RF, CTRL |  | cables re-calibration
33 | Cavity spectra | 0.5 |  | RF |  | fundamental and HOM spectra |  |  |  | VNA
34 | Cold coupler re-conditioning | 0.5 |  | RF |  | conditioning coupler | reach full power, pulse length |  |  |  | RF source
35 | Measurement Q0 | 1 |  | RF | a | Qloaded (3 dB bandwidth) |  |  |  | VNA | RF source
[5 empty] | b | Qloaded (decay technique) |  |  |  | pulsed SEL
[5 empty] | c | Q0 (emitted power technique) |  |  |  | pulsed SEL | RF source
36 | Measurement Gradient | 1 |  | RF | a | Eacc measurement | nomial gradient, max gradient |  |  | pulsed SEL | RF source
[5 empty] | b | X-ray emission |  |  |  | pulsed SEL, Labview
[5 empty] | c | electron activity in coupler
Week starting 20 February
37 | Field emission |  |  |  |  | Onset and level of field emission
38 | Multipacting |  |  |  |  | Onset and level of Multipacting
39 | RF Compensation |  |  |  |  | Stabilization of the cavity field with LLRF
40 | Dynamic RF losses | 1 |  | CRYO, RF | [6 empty] | RF source
41 | Lorenz detuning | 1 |  | RF |  | LDT measured in a pulsed test |  |  |  | Signal generator driven loop
42 | Microphonics | 1 |  | RF, CRYO
Week starting 27 February
43 | Measurement Q0 |  |  |  |  | repeat Q0 measurement at 4K
44 | Repetition of any earlier measurements as deemed necessary
Week starting 6 March
45 | Warm-up | 5 |  | CRYO | a | warm-up of cryomodule
[5 empty] | b | cavity frequncy checking |  |  |  | VNA,Labview
open the main bunker gate
Week starting 13 March
46 | Opening HNOSS | 1 |  |  | a | opening main doors
[5 empty] | b | removal thermal shields
47 | Disconnect | 2 |  |  | a | RF
[5 empty] | b | Instrumentation
[5 empty] | c | Vacuum
[5 empty] | d | Cryogenics
[5 empty] | e | Cooling water
48 | Power coupler disconnection | 2 |  |  | a | disconnect waveguide
[5 empty] | b | disconnect door knob
[5 empty] | c | remove antenna
Week starting 20 March
49 | Cavity disconnection | 2 |  |  | a | install insertion tool
[5 empty] | b | remove power coupler bellows
[5 empty] | c | move cavity from tie rods onto insertion tool
[5 empty] | d | roll cavity out
50 | Move out of bunker | 0.5 |  |  |  | Move cavity outside bunker
51 | Cleaning cavity | 2 |  |  | a | remove MLI
[5 empty] | b | remove instrumentation
[5 empty] | c | remove heaters
Week starting 27 March
51 | Inspection | 2
52 | Prepare for transport | 3
Week starting 3 April
53 | Transport from Uppsala to Orsay | 3 |  |  |  | Transport