## Slide 1: Teleconference ACS – FREIA 31th May 2017
Agenda:
Presentation Spoke Cavity Testing in HNOSS
Manufacturing follow-up
Control and command
Planning

## Slide 2: Manufacturing follow-up
Valve box
  All components are available, excepted several pipes which are bending by a subcontractor.
Cryostat
  CD received the vacuum vessel
  The pressure vessel is in welding stage
  The pit is prepared to install the vessel for assembly
Magnet insert
  The manufacturing drawings will be finished soon and will be send for production after validation by ACS and UU.
Pressure vessel waiting for X-ray control
Preparation of the pit

## Slide 3: Control and Command
Connection boxes (inserts)
  Cables between connection box on insert and instrumentation box in the pit will be joined to the connection box
  When changing an insert the cables will be disconnect from the instrumentation box then pose on storage racks on the insert

## Slide 4: Control and Command
Instrumentation box in the pit
  It gathers cables from the insert connection box and instrumentation towers
  > important number of connectors, important size
  > under study by Technergie to select the optimal box (may be custom-made)
  Implementation?

## Slide 5: Control and Command
Connection boxes
  Cryostat, inserts, pit: stainless steel
  Valve box: PVC
  New quotation made according to last comments
Special cables
  Directly connected to the electrical cabinet (cg: coaxial), except if can be connected to the connection box (cg: AMI)

## Slide 6: Control and Command
Programming
  ISII-Tech presented a draft software to CD and ACS
  ISII-Tech will send the scheme to ACS for validation
  2 tests are foreseen at the end of June and at the end of July to check every sequences

## Slide 7: Planning
Valve box
  W25: reception of components
  W26: heat exchanger 4K
  W27: thermal shielding
Cryostat
  W22: cleaning, assembly, welding and control (X-ray) of the pressure vessel
  W23: welding of cooling system and top lid on pressure vessel
  W24: assembly of equipment
Simulator
  W22: sending the nomenclature
  W23: purchase of components
  W27: start of manufacturing
Magnet insert
  Heat exchanger Lambda HX683: 18 weeks of manufacturing

## Slide 8: Planning
C&C and cabling:
  W36: start of workshop pre cabling
    Duration: 1 months
  Tests in October
Electrical design
  2 weeks of delay + summer holidays