## Slide 1: Uppsala University Contract UH2015/09 - UA2016/05 Job nr. 5973/7200
Vertical Cryostat GERSEMI
4th follow-up meeting
06/07/2017

## Slide 2
JOB STATUS
General planning
  Cryostat
    Previous target: 27/06
    New target: 19/07
  Valves Box
    Previous target: 28/06
    New target: 03/08
  Simulator box
    Previous target: 19/07
    New target: 20/09
  Workshop tests
    Previous target: 22/09
    New target: 15/11
  Onsite tests
    New target: November 2017 to March 2018

## Slide 3
JOB STATUS
WP2: cryostat status
  Issues:
    Trouble with cooling circuits
  Mitigation:
    Design update to use another cooling circuit type

## Slide 4
JOB STATUS
WP3: magnet insert
  Issues:
    Copper heat exchanger manufacturing
    Current lead still not defined

## Slide 5
JOB STATUS
WP5: valves box
  Issues:
    Resources and tooling difficulties on some very complex bending
  Mitigation:
    Qualification of new subcontractor for 3D bending

## Slide 6
JOB STATUS
WP6: transfer lines
  Multiline procurement almost completed
  Multiline manufacturing file released to the workshop
  Next step single lines and general integration of the GERSEMI Project in FREIA Hall:
    Needs definition of current leads to define the last components
    Needs to check the 3D model of the water heat exchanger compared with the already built one

## Slide 7
JOB STATUS
Procurement issues:
  Cernox: calibrating machine is in repair by IPNO
  Electrical studies are hold to JB decision
  Some components are not defined (needs current lead design to be finished