## Slide 1: Teleconference ACS – FREIA 17th October 2017
Agenda:
Manufacturing follow-up
Planning
Issues
Future tasks

## Slide 2: Manufacturing follow-up
Cryostat
  Dewar piping ongoing (LHe circuit done)
  Thermal shield : cooling pipes validated (He leak test and thermal shock)
  Instrumentation and wiring starts this week
Magnet insert
  Manufacturing drawings under final review
  Top lid is under cutting, required parts are in stock or already ordered
  Manufacturing starts W43 (end of October)
Liquid insert
  Waiting for final cabling (W42)

## Slide 3: Manufacturing follow-up
Valve box
  Assembly of piping done
  Heaters and thermometers set on the thermal shield, 4k pot and heat exchanger
  Waiting for final cabling (W42)
Transfer lines
  Manufacturing of the single line and multiline under way
Simulator box
  Manufacturing drawings under final review
  Manufacturing started this week (W42)

## Slide 4: Control and Command follow-up
Control system design
  Programming done, waiting for test with GERSEMI systems
Control system procurement
  Junction boxes done
  Electrical cabinet still at Technergie, not necessary yet

## Slide 5: Planning: GERSEMI
 | 2017 |  |  |  |  |  |  |  |  |  |  |  |  | 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  | 
 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
junction box manufacturing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
electrical wiring of VB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
electrical wiring of liquid insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
electrical wiring of VC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
simulator manufacturing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Simulator mechanical testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Simulator electrical wiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet insert manufacturing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet insert mechanical testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet insert wiring |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
final electrical wiring of control cabinet & test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
control cabinet & automaton test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
factory acceptance test with simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
control cabinet & automaton test with magnet insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
packing of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
installation of project onsite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
cryogenic tests with simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
final installation of project without simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
acceptance tests with liquid insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
acceptance tests with magnet insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: Issues
Cernox
  IPN: cernox in stock but not the right shape; checking possibility to manufacture “adaptor” parts and do the wiring
  Manufacturing this week (W42), delivery next week (W43)
Wiring
  Delay for VB and liquid insert

## Slide 7: Future tasks
Commissioning tests
  Final mechanical tests
    Helium leak test after assembly
      All circuits of VB with valves
  Electrical tests
    Electrical insulation
    Resistance
  Cryogenic test
    VB+simulator