## Slide 1: Teleconference ACS – FREIA 20th February 2018
Agenda:
Manufacturing follow-up
Control and command status
Planning
Commissioning tests
Installation at Uppsala

## Slide 2: Manufacturing follow-up
Magnet insert:
  Welding of the top plate
  Welding of the thermal screens
  Support assembly
  Internal components
  HX683
Issues:
  Copper tube supply delayed to March
  New flanges required for the vacuum box

## Slide 3: Control and Command status
ISII-tech was present during the tests providing:
  Formation
  Technical support
Technergie still have few work to complete on the vertical cryostat
Due to the delay of the magnet insert manufacturing, ACS asked CD to send the electrical cabinet with the cryostat,
  Electrical tests on the magnet insert will be done with electrical test boxes
  Mechanical tests (leak test, thermal shock, vacuum) doesn’t require the electrical cabinet

## Slide 4: Planning: GERSEMI
 | 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
magnet insert manufacturing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
magnet insert mechanical testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
final electrical wiring of control cabinet & test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
vertical cryostat electrical wiring repair |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
control cabinet & automaton test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
factory acceptance test with simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
control cabinet & automaton test with magnet insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
packing & delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- vertical cryostat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- valve box & simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- control cabinet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- magnet insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
onsite installation of project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- vertical cryostat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- valve box & simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
- control cabinet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
onsite cryogenic tests with simulator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
onsite final installation of project with liquid insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
onsite acceptance tests with liquid insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
onsite acceptance tests with magnet insert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Planning: GERSEMI
Week 08
  Monday: MLI final check
  Wednesday-Thursday: carting VB + VC + simulator
Shipping : end of W08 – beginning W09
Delivery at Uppsala: early March
Ongoing tasks
  Disassembly
  Packaging
  Listing, documentation
Additional:
  VC thermal shield modification (baffle, paint)
CD preparation
List of repair (to be done after shipping)

## Slide 6: Commissioning test
Final mechanical tests:
  He leak tests vessels, circuits and valves
  Assembly of the multiline L012 (VC side)

## Slide 7: Commissioning test
Simulator allows the control of the following sequences (liquid mode):
  1 VB, conditioning LHe circuit
  3 VB, conditioning She circuit
  5 VB thermal shield cooling
  8 LHe level measurement
  9 VB cooling +4K tank control level
  10 cavity cooldown
  12 cavity in operation @4K
  14 cavity in standby @40K
  21 VB warm-up
  22 VC warm-up
  24 VC isolated or connected to He recovery circuit
  25 VB isolated or connected to He recovery circuit
Some sequences couldn’t be tested in CD workshop due to the absence of external components:
  LHe production
  Double reheater + recovery system

## Slide 8: Installation at Uppsala
Time planned for installation?
  Mechanical
  Electrical connections
  Transfer lines
ACS presence for:
  Assembly validation
  Commissioning tests

## Slide 9: Thank you for your attention
Q&A