## Front Page
FREIA Laboratory
Dept. of Physics and Astronomy
Uppsala University
Document No.: |  | Experiment Document No.: |  | Created: |  | 2017-09-18 | Page: | 1
|  |  |  | Modified: |  | 2018-03-13 | Rev. No.:
Engineering Specification
HNOSS
Cavity Package Test
ESS High Beta Elliptical Cavity Prototype
| Prepared by |  | Checked by |  |  |  | Approved by
R. Ruber
J. Eriksson
L. Hermansson
R. Santiago Kern
Distribution List

## Procedure
ESS High Beta Elliptical Cavity Prototype
Step | Process or Check Item | Overall Time [days] | In Bunker [days] | Team | Sub-step | Work Description | Acceptance Criteria | Check Sheet | Parts | Tools and Instruments | Utilities and Services
Required Parts and Equipment
| Rotation table |  |  | CEA
| Rotation table support |  |  | Uppsala
| HNOSS table |  |  | Uppsala
| Insertion support |  |  | Uppsala
| Mobile clean room |  |  | Uppsala
| Clean vacuum bellows |  |  | Uppsala
1 | Shipment from to Uppsala | 2 | [8 empty] | mobile crane, fork lift
2 | Arrival, unloading | [9 empty] | mobile crane, fork lift
3 | Unpacking | 0.5 |  | MECH | a | opening box
[5 empty] | b | read-out shock data logger
4 | Inspection | 1 |  | MECH | a | external inspection | no visual damage
[5 empty] | b | mechanical parts
[5 empty] | c | instrumentation connections | electrical |  |  | multimeter, test box
5 | Cold tuner | 2 |  | CEA | a | place cavity on turning table |  |  | Rotation table & support
[5 empty] | b | rotate cavity | block position
[5 empty] | c | install cold tuner
[5 empty] | d | rotate cavity
6 | Portable clean room | 1 |  | VAC | a | install portable clean room for clean air flow |  |  |  |  | portable clean room
[5 empty] | b | start clean air flow along cavity vacuum connection
7 | Cavity vacuum | 0.5 |  | VAC | a | ensure clean air flow along cavity | particle count = 0 |  |  |  | portable clean room
[5 empty] | b | clean connection surfaces
[5 empty] | c | connect vacuum line |  |  | vacuum bellows
8 | Instrumentation | 2 |  | MECH | a | install temperature sensors |  |  | 8 cernox
[5 empty] | b | install heaters (2x) |  |  | 4 heaters
9 | Thermal insulation | 0.5 |  | MECH |  | install MLI on the cavity
10 | Test insertion | 2 |  | MECH | a | put cavity on the insertion tooling
| If applicable, tbc |  |  |  | b | roll cavity inside HNOSS
[5 empty] | c | verify final position
[5 empty] | d | verify vacuum connection
[5 empty] | e | verify cryogenic connections
[5 empty] | f | roll cavity out from HNOSS
11 | Insertion | 2 |  | MECH | a | roll cavity inside HNOSS |  |  |  | insertion tool
[5 empty] | b | lower cavity to final position
[5 empty] | c | fix cavity to bottom tie rods/table |  |  |  | tie rods
[5 empty] | d | adjust cavity position | level, rotation
[5 empty] | e | attach top tie rods | if applicable
[5 empty] | f | attach thermalization of tie rods | if applicable
12 | Power coupler | 2 |  |  | a | put vacuum bell for power coupler into position
[5 empty] | b | verify alignment | level, rotation
[5 empty] | c | final adjustment cavity position
[5 empty] | d | fix vacuum bell
13 | Cavity cryogenics | 2 |  | CRYO | a | LHe (pre)cooling line
[5 empty] | b | LHe inlet/outlet line
[5 empty] | c | LHe level probe
[5 empty] | d | fix cryogenics lines to prevent cavity movement | if needed
[5 empty] | e | install MLI on cryogenic lines
14 | Power coupler cryogenics | 0.5 |  | CRYO | a | power coupler cryo line (SHe) input
[5 empty] | b | power coupler cryo line (SHe) output
15 | Leak test | 0.5 |  | CRYO |  | leak test of the cryogenics line |  |  |  | vacuum leak tester
16 | Portable clean room | 1 |  | VAC | a | install portable clean room for clean air flow |  |  |  |  | portable clean room
[5 empty] | b | start clean air flow along cavity vacuum connection
17 | Cavity vacuum | 0.5 |  | VAC | a | blow air flow along connection surfaces | zero particle count |  | top gun (ionizing air gun) |  | portable clean room
[5 empty] | b | start gas nitrogen flow through vacuum line | flow = 10 l/min |  | Swagelock Ultrahigh-Purity (UHP) Gas Filters (SCF Series
[5 empty] | c | ensure clean gas flow and surfaces | particle count = 0
[5 empty] | d | stop nitrogen gas flow | flow = 0
[5 empty] | e | connect vacuum line
18 | Leak test | 0.5 |  | VAC |  | vacuum line | pump and pressurize lines
19 | Pressurize cavity | 0.5 |  | CEA | a | pressurize vacuum line (b/w cavity and pump) | nitrogen gas
[5 empty] | b | very slow opening of the valve to the cavity
20 | Cold tuner | 0.5 |  | CEA | a | finalize connection cold tuner
[5 empty] | b | verify operation cold tuner
[5 empty] | c | install MLI at the cold tuner side of the cavity
21 | Power coupler | 4 |  | CEA | a | install antenna | CEA procedure |  |  | CEA tooling
[5 empty] | b | install doorknob
[5 empty] | c | connect cooling water lines
[5 empty] | d | leak check cooling water
22 | RF distribution | 2 |  | RF |  | connect waveguide to doorknob
23 | Vacuum pumping | 0 |  | VAC |  | open cavity vacuum valve | < xxx
24 | Instrumentation | 1 |  | CRYO | a | connect cavity instrumentation |  |  |  | multimeter, test box
[5 empty] | b | connect cold tuner instrumentation
[5 empty] | c | connect power coupler instrumentation
[5 empty] | d | instrumentation check
25 | Measurement | 1 |  | RF | a | S parameter measurement | Qext |  |  | VNA
[5 empty] | b | cavity frequency measurement |  |  |  | Labview, VNA
26 | Closure HNOSS | 1 |  | MECH | a | close thermal shield
[5 empty] | b | close flanges
[5 empty] | c | close main doors
27 | HNOSS vacuum | 0 |  | MECH |  | start HNOSS vacuum pumps
28 | Close bunker | 2 |  | MECH | a | close bunker roof
[5 empty] | b | close main bunker gate
29 | RF conditioning | 2 |  | RF |  | power coupler conditioning | reach full power, pulse length |  |  |  | RF source
30 | Measurement |  |  | RF |  | start cavity frequncy checking |  |  |  | VNA, Labview
31 | Cool down | 4 |  | CRYO | a | cool down thermal shield with LN2 |  |  |  |  | LN2
[5 empty] | b | cool down to 4 K |  |  |  |  | Liquefier
[5 empty] | c | stabilize at 4 K
[5 empty] | d | cool down to 2 K |  |  |  |  | 2K pumps
[5 empty] | e | cooling coupler |  |  |  |  | SHe pumps
32 | Cryogenic optimization | 2 |  | CRYO | a | filling w and w/o regulation
[5 empty] | b | FPC cooling dependence on heat load
[5 empty] | c | max heat power applied to cavity
33 | Cavity frequency | 1 |  | RF |  | sensitivity to helium pressure fluctuation |  |  |  | VNA, Labview
34 | CTS Calibration | 0.5 |  | RF, CTRL |  | tuning range of the slow step tuner at cold temperature |  |  |  | Labview, SEL, frequency meter
35 | RF Calibration | 0.5 |  | RF, CTRL |  | cables re-calibration
36 | Cavity spectra | 0.5 |  | RF |  | fundamental and HOM spectra |  |  |  | VNA
37 | Cold coupler re-conditioning | 0.5 |  | RF |  | conditioning coupler | reach full power, pulse length |  |  |  | RF source
38 | Measurement Q0 | 1 |  | RF | a | Qloaded (3 dB bandwidth) |  |  |  | VNA | RF source
[5 empty] | b | Qloaded (decay technique) |  |  |  | pulsed SEL
[5 empty] | c | Q0 (emitted power technique) |  |  |  | pulsed SEL | RF source
39 | Measurement Gradient | 1 |  | RF | a | Eacc measurement | nomial gradient, max gradient |  |  | pulsed SEL | RF source
[5 empty] | b | X-ray emission |  |  |  | pulsed SEL, Labview
[5 empty] | c | electron activity in coupler
40 | Field emission |  |  | RF |  | Onset and level of field emission
41 | Multipacting |  |  | RF |  | Onset and level of Multipacting
42 | RF Compensation |  |  | RF |  | Stabilization of the cavity field with LLRF
43 | Dynamic RF losses | 1 |  | CRYO, RF | [6 empty] | RF source
44 | Lorenz detuning | 1 |  | RF |  | LDT measured in a pulsed test |  |  |  | Signal generator driven loop
45 | Microphonics | 1 |  | RF, CRYO
46 | Slow tuner range measurement | 1
47 | Tuner measurements (LU) | 1
48 | Measurement Q0 | 1 |  | RF |  | repeat Q0 measurement at 4K
49 | Power coupler cooling |  |  | CRYO, RF |  | measure and regulate the required power coupler cooling water
50 | Repetition of any earlier measurements as deemed necessary
51 | Warm-up | 5 |  | CRYO | a | warm-up of cryomodule
[5 empty] | b | cavity frequncy checking |  |  |  | VNA,Labview
open the main bunker gate
52 | Opening HNOSS | 1 |  | MECH | a | opening main doors
[5 empty] | b | removal thermal shields
53 | Disconnect cavity | 2 |  | RF | a | RF
|  |  |  | CRYO | b | Instrumentation
|  |  |  | MECH | c | Vacuum
|  |  |  | CRYO | d | Cryogenics
|  |  |  | MECH | e | Cooling water
54 | Disconnect power coupler | 2 |  | RF | a | disconnect waveguide
[5 empty] | b | disconnect door knob
[5 empty] | c | remove antenna
55 | Removal cavity | 2 |  | MECH | a | install insertion tool
[5 empty] | b | remove power coupler bellows
[5 empty] | c | move cavity from tie rods onto insertion tool
[5 empty] | d | roll cavity out
56 | Move out of bunker | 0.5 |  | MECH |  | Move cavity outside bunker
57 | Cleaning cavity | 2 |  | CRYO | a | remove MLI
[5 empty] | b | remove instrumentation
[5 empty] | c | remove heaters
57 | Inspection | 1 |  | MECH
58 | Prepare for transport | 2 |  | MECH
59 | Transport | 3 |  | MECH |  | Transport
| TOTAL Time Spend | 72 | 0
| For 1 cavity | 72 | 0 | days
|  | 14.4 | 0 | work weeks
|  | 3.4286 | 0 | months |  | national holidays and vacation time not taken into account