## Slide 1: CERN SM18 test stand news
Marta Bajko, CERN
June 2019

## Slide 2: Content of my talk
SM18 test facility development for HL-LHC
Road Map of construction work
Testing at CERN in SM18
TNA ARIES
Summary

## Slide 3: Summary of testing for the HL-LHC
WP3: Test stands are operational for model magnets ( Cluster D and HFM) and ready for prototypes ( Cluster A),
Yet to be built on both the HFM and Cluster D the secondary low current circuits with EE for correctors ; upgrade Cl A with low current and CL for 2 kA, build a second test stand (Cluster F) to insure redundancy and reduce risk needed for 2020. Interfaces with mechanical and hydraulically connections are needed for D1, D2 also!
WP6A: Test stands for SC Link demonstrator ( 60 m) is operational for cryostat testing.
Identified test stations for measurement of series component (leads and SC Links). Conceptual work started. Detailed and design work to follow - 2018 and 2019
WP7: QPS system implemented for parallel working conditions with present protection system on cluster D.
Is planned to be implemented this year on Cluster C in the same way before implementing for 2020 exclusively that system on Cluster F.
WP16: Test stand for HL-LHC IT STRING is in preparation.
WP11: Test stand is operational for model magnets and the modifications are ongoing for the prototype and series measurements. To be completed this year.
Demineralised water, new overhead crane and new control room are operational.
Primary water, cryogenic cooling and the upgrade of the whole electrical distribution is ongoing. Operation foreseen 2019.
Pumping capacity upgrade is proven that is needed. Strategy is in place.

## Slide 4: Road Map of SM18 test benches: 2018-2020
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
HFM and Cluster D for Q2 and D2 corrector magnets with two circuits (WP3)
Bench A1 for Q2 type cryo magnets
( WP3)
Bench F1 for Q2 type cryo magnets and nQDS
(WP3/ WP7)
Bench F2 for Sc link and nQDS
( WP6A/WP7)
Modify for CL
Feed Box for CL test on Cluster G (WP6A)
Cluster J for HL-LHC IT STRING ( WP16)
Cluster J
Service upgrade:
  He Liquefier
  Transformer
  Water cooling
Safety improvement
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
Mid 2019
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE

## Slide 5: Cluster G development
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
HFM and Cluster D for Q2 and D2 corrector magnets with two circuits (WP3)
Modify for CL
Feed Box for CL test on Cluster G (WP6A)
Cluster J
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
Mid 2019
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE

## Slide 6: Cluster A and F development for magnets
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
Bench A1 for Q2 type cryo magnets
( WP3)
Bench F1 for Q2 type cryo magnets and nQDS
(WP3/ WP7)
Modify for CL
Cluster J
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
Mid 2019
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE

## Slide 7: Cluster F development for superconducting links
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
Bench F2 for Sc link and nQDS
( WP6A/WP7)
Modify for CL
Cluster J
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
Mid 2019
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE

## Slide 8: Cluster F development for superconducting links
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
Modify for CL
Cluster J
This will allow us to test the Sc Link systems
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
End 2018
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Service UPG
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE
SC Link
DFX
DFHx
Module 1
DFHx
Module 2
Réchauffeur
Alim 20 kA
Cluster F
TOP VIEW
Cluster D
Cluster E
Cluster F
Current leads
2 x 18kA
2 x 13kA
3 x 7kA
6 x 2kA
SC Link 17m
Alim 13 kA
Cluster C
Alim 13 kA
Cluster E

## Slide 9: HL-LHC IT STRING test stand and service upgare
Cluster G
Cluster D
Cluster A
Cluster F
Install secondary circuit (structure, WCC, EE)
Install secondary circuits for 2 kA
(CC, PC, EE, CL)
Change CL in the feed box, install CC and PC of 2 kA
Install 20 kA, 2kA PC, WCC, CC, EE, structure, DFX, DFH, QDS
Modify QDS ( WP11)
Modify for CL
Cluster J for HL-LHC IT STRING ( WP16)
Cluster J
Service upgrade:
  He Liquefier
  Transformer
  Water cooling
Safety improvement
June 2018
Metallic structures for magnet preparation zone Cluster D and G
Secondary circuit for HFM ( metallic structure , WCC, Switch and Dump), Cluster C modification for 11T
Summer 2018
Mid 2019
Secondary circuit for Cluster D for proto MCBXFA/B (CC, PC, Switch and Dump)
February 2020
End 2020
Cluster F for Sc link series
Mid 2019
Cluster G Feed Box and diode cryostat modification for CL test
January 2021
HL-LHC IT STRING
Cluster A, F, B,E for Q2,D2 magnets: PC, CL, WCC,EE
See the dedicated presentation on this subject

## Slide 10: Testing in SM18
We do in average 40 test per year with an increase in capacity of up to 20-30% per year
HFM
Cluster D
Siegtal
LONG
Diodes and Leads

## Slide 11: Trans National Access @ CERN MagNet within ARIES

## Slide 12: WP9 – TNA : MagNet
          5 projects were submitted for approval
          4 approved and 1 in evaluation process
          4 of them has been already performed tests
Facility | No. of projects Y1 | Total no. of projects Annex 1 | No. of users Y1 | Total no. of users Annex 1 | No. of access units Y1 | Total no. of access units Annex 1
MagNet | 4 | 8 | 27 | 40 | 944 | 1,920
Gersemi | 0 | 8 | 0 | 56 | 0 | 2,880
TNA is composed by two laboratories: CERN ( CH) and FREIA (S).
MagNet (@CERN) is operational
GERSEMI (@FREIA) is starting Hardware Commissioning with possible testing by the end of the year.

## Slide 13
Summary
CERN SM18 test facility is essentially developed for the HL –LHC project but
We do test for ATIRES TNA project for external members also
Our installations covers test stand for :
  Superconducting magnets
  Superconducting and normal conducting current leads
  Superconducting links
  HL-LHC IT STRING
Construction work is still ongoing till end 2020 in SM18
Today 5 vertical test stands, 8 horizontal benches and 1 feed box is operational
A cryogenic liquid production is under upgrade and we expect 35 g/s extra wrt 25 g/s we have today from 2020
The operation is ongoing in parallel with the upgrade and construction work