## Slide 1: Preparation for Series CM
Hardware:
RF station:
DB station:
  Repair the G1 power supply
Both stations are ready to run power next week
Doorknob
Dismount of the doorknob is on going

## Slide 2: Preparation for Series CM
Software:
LLRF upgrade
LLRF1 upgrade is on going this week
Will first test the upgraded LLRF1 with Electrosys
Test with both chains of LLRFs and RF stations simultaneously

## Slide 3: List of minimum tests
1 | Central cavity frequency | to reach 352.21MHz within step tuner linear zone provide corresponding step tuner setting
2 | Loaded Q | both 3 dB BW and decay measurement, 1.75-2.85 E5
3 | Steady state heat load | 
4 | Dynamic heat load for both cavities from 8 to 12 MV/m | less than 5 W per CM at nominal Eacc
5 | Q0 | calorimetric measurement higher than 1.5 e 9 at 9MV/m
6 | Reach gradient of 12 MV/m | quench point if it is lower than 12 MV/m
7 | Tuning range of the slow step tuner | provide parameter of full steps
8 | Frequency shift due to cool down | 
9 | Stabilization of the cavity field with LLRF using both RF and piezo tuner compensation | optional only for 1st CM
10 | Stabilization of the CM for long-term operation | only for 1st CM
11 | Onset and level of field emission | 
12 | Multipacting | 

## Slide 4: method for the main test items
1 | Central cavity frequency | S parameter measurement via vector network analyzer
2 | Loaded Q | Both 3 dB BW and decay measurement
3 | Static heat load | Calorimetric measurement via the flowmeter placed after the sub-atmospheric pumps
4 | Dynamic heat load for both cavities from 8 to 12 MV/m | 
5 | Q0 | PID/Open loop operation with ESS LLRF system
6 | Reach gradient of 12 MV/m | 
7 | Tuning range of the slow step tuner | S parameter measurement via vector network analyzer
8 | Frequency shift due to cool down | 
9 | Stabilization of the cavity field with LLRF using both RF and piezo tuner compensation | PID operation with ESS LLRF system
10 | Stabilization of the CM for long-term operation | 
11 | Onset and level of field emission | 
12 | Multipacting | Conditioning with ESS LLRF open loop / auto-conditioning LabView program

## Slide 5
VNA
Open loop
SEL ( back up)
ESS LLRF PID
CRYO
Warm test | Cool down | Cold test | Warm up
Central cavity frequency Qe | Frequency shift due to cool down Pressure sensitivity | Coupler cold conditioning | 
 |  | Central frequency Loaded Q and Qe | 
 |  | Tuning range of the slow step tuner | 
 |  | Cavity conditioning | 
Coupler warm conditioning |  |  | 
 |  | Steady heat load of CM | 
 |  | Q0 Dynamic heat load Reach 9 MV/m | 
 |  | Stabilization of the cavity field | 

## Slide 6: Modification after the prototype test
Hardware | Replacement of cryogenic jumper
 | Cabling adoption
 | Implementation of the terminal box based on the series CM cable logic
 | Application of two pumping cart simultaneously
 | Repair of Electrosys RF station
Software | Update of ESS LLRF firmware for synchronization
 | Development of quench detector/interlock
Further improvement | Auto-conditioning program for FPC (suitable for 24/7 running)
 | Top panel for both operator and expert (suitable for shift)

## Slide 7: Critcal spare parts
TH595 tetrode tube for RF station
Anything that considered as critical part need to be added?

## Slide 8: To do list
number | item | Person in charge | status
1 | Get back and install G1 power supply for Electrosys | Rolf, Tord | close
2 | Test DB and Electrosys station to full power | Rolf, Tord, Han, Michael | close
2 | Ask for shock senor reader preparation, test box, documentation | Roger | close
3 | Tuner control software validation | Kjell | opening
4 | Dismount of doorknob | Lars | On going
5 | Validation of vacuum pumping cart | Lars | On going
6 | Overall check with the LLRF/software | Han, Tor, Kjell | opening
7 | Cryogenic procedure | Lars, Esat | opening
8 | Test documentation | Han | close
9 | Documentation for TRR | Roger, Han | On going
10 | Factory calibration of key devices (VNA) Repair of R&S oscilloscope | Tor | opening
Before CM arrival:

## Slide 9: To do list
number | item | Person in charge
1 | Readout information of shock sensor and vacuum | Akira, Han
2 | Visual checking of CM | Han, Akira
3 | Cavity frequency at room temperature | Han
4 | Sensor/cable continuity (test box) | Akira
5 | FPC and doorknob installation | Lars
6 | Vacuum pumping system installation | Lars
7 | Calibration of the pressure sensors/MKS | Konrad
After CM arrival: