## DFHX Assembly Procedure
DFHX ASSEMBLY PROCEDURE
STEEP | DESCRIPTION | COMMENTS | TOOLINGS | ASOCIATED DRAWINGS | SCENE/ DIAGRAM POSITION | ASSEMBLY - WHO? | PICTURE
SC-LINC CONNECTION
1 | Install the "Main Frame ST1295103" and the "Extension-Main Frame" horizontally, respecting flatness and alignment parameters.
2 | In an horizontal table, assembly the "CONNECTION FLANGE TO LINK LHCDFHX_0021" and the "FRAME LHCDFHX_0038". Check correct positioning and perpendicularity specifications. |  |  |  | 01.A).-
3 | Install the subassembly in the "Main Frame", checking geometrical specifications, perpendicularity, alingment with the "Main Frame", … |  |  |  | 01.B).-
4 | A.- On the "Main Frame ST1295103" instal the "Support cradle assy ST1348198_01". B.- Slide it underneath the "VACUUM CHAMBER_1 ASSEMBLY LHCDFHX_0040" and adjust it to the correct height to hold it. |  | Support cradle assy - ON (x1) |  | 01.C).-
5 | A.- On the "Main Frame ST1295103" instal TWO "Support cradle assy ST1348198_01". B.- On the "Main Frame ST1295103" instal TWO "Support cradle assy - for bellows ST1348198_02". C.- Over them, install the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042" and the "VACUUM CHAMBER FLEXIBLE LHCDFHX_0006". D.- On the "Main Frame ST1295103" install, with their sliding system, the "VACUUM CHAMBER TO SLEEVE LHCDFHX_0008" and the "VACUUM CHAMBER CENTRAL LHCDFHX_0024". E.- Align and clamp them to get a preadjustement of the these subassemblies. F.- Remove all the subassembies until retourn to the situation from steep 4. |  | Support cradle assy - ON (x2) (Total = x3) Support cradle assy - for bellows - ON (x2) Support cradle assy - for bellows - OFF (x2) Support cradle assy - OFF (x2) (Total = x1) |  | 01.C2).-
6 | Unscrew the "VACUUM CHAMBER_1 ASSEMBLY LHCDFHX_0040" from the "CONNECTION FLANGE TO LINK LHCDFHX_0021", and open a gap by scrolling the "VACUUM CHAMBER_1 LHCDFHX_0041" backwards (in direction to the "FRAME LHCDFHX_0038") 234mm. * Hereinafter Cryogenic Box = CB1. |  |  |  | 01.C).- 01.D).-
7 | Instal "TOOLING 1", and then, the "FRONT PART CRYOGENIC BOX LHCDFHX_0047", checking correct positioning (PIN in upper position in the Front Plate). Install "Welded interface SC-LINK - DFHx LHCDSH_C0001". | Notice that the cable is not yet installed. | TOOLING 1 - ON SPACERS BETWEEN SC-LINC AND THE HELIUM CHAMBER FRONT PLATE |  | 01.E).- 01.F).-
HELIUM CHAMBER "WHITE" ASSEMBLY TO ALIGN CORRECTLY THE SC-LINC CONNECTION BEFORE WELDING
8 | Install "TOOLING 2" (sliding support carriage - TO BE DESIGN) for "DISTRIBUTION PLATE ST1228235_01". |  | TOOLING 2 - ON DISTRIBUTION PLATE CB1 - SLIDING SUPPORT |  | 02.A).-
9 | Install "DISTRIBUTION PLATE ST1228235". Check alignment with "FRONT PART CRYOGENIC BOX LHCDFHX_0047". |  |  |  | 02.A).-
10 | Install "TOOLING 3" (sliding support carriage - TO BE DESIGN) for "CENTRAL PART CRYOGENIC BOX 1&2 LHCDFHX_0053". |  | TOOLING 3 - ON REAR PLATE CB1 - SLIDING SUPPORT |  | 02.A).-
11 | A.- Install "ASSEMBLY REAR PART CRYOGENIC BOX. ST1228237". B.- Uninstall the CB1 Sleeve-2 (x4), "SLEEVE 1/4-BOX 1 LHCDFHX_0076". C.- Install the CB1 Support Shaft: "SHAFT SUPPORT LHCDFHX_0093" + "SHAFT MACHINED LHCDFHX_0118" + "MALE SHAFT MACHINED LHCDFHX_0119". |  | TOOLING 20 - ON PREINSTALED 3 BARS TO FIX TEMPORARY THE CRYOBOX 2 FRONT PLATE |  | 02.A).-
12 | Check the alignment and the rest of the geometrical specifications before. Adjust with "TOOLING 1" if necessary. |  |  |  | 02.A).-
13 | Install "TOOLING 4" (Temporary Support Bridge - TO BE DESIGN) for the CB1 Support Shaft | OPTIONAL | TOOLING 4 - ON SUPPORTING BRIDGE FOR HE CHAMBER, CB1 & CB2. |  | 02.B).-
14 | Unscrew the "SHAFT BOX-1 LHCDFHX_0055" (x4) from "PLATE_FRONT PART LHCDFHX_0046" that had been installed for the alignment of "FRONT PART CRYOGENIC BOX LHCDFHX_0047". Open the "CENTRAL PART CRYOGENIC BOX 1&2 LHCDFHX_0053" as much as possible by also moving the "TOOLING 4". |  |  |  | 02.C).-
15 | Weld "Helium Flange (DFH) ST1184762" to "PLATE_FRONT PART LHCDFHX_0046" of CB1. Notice that the cable is not yet installed. | Notice that the cable is not yet installed. |  |  | 02.C).-
16 | WELDING TEST. |  |  |  | 02.C).-
17 | Install MLI around the "FRONT PART CRYOGENIC BOX LHCDFHX_0047" surrounding also the "Welded interface SC-LINK - DFHx LHCDSH_C0001". |  |  |  | 02.C).-
1ST CHAMBER - HELIUM CHAMBER REAR PLATE AND CABLE INSTALLATION
18 | Install "FIL BOX 1 LHCDFHX_0097". |  |  |  | 03.A).-
19 | A.- Insert the cable. B.- Install the "TOOLING 5". C.- Using a winch ("TOOLING 5"), pull the cable until the cable has reached its final position (Cryobox 2 Splice boxes, hereinafter Cryobox 2 = CB2) with extra length: 3260mm from the edge of the "ASSEMBLY FRONT PART CRYOGENIC BOX. ST1228227", which includes 400mm extra length. D.- Remove the "TOOLING 5. |  | TOOLING 5 - ON / OFF WINCH FOR CABLE PULLING |  | 03.A).-
20 | Open the cable package and split the cables, in order to pass through its corresponding holes at the CB1 Rear Plate Assy (do NOT unwrap the 2 packaged 2kA cables). Cables for 14/18KA and 7kA,can be cut with extra legth to make it easier to introduce them in their respective channels in the distribution plate and th GB1 Rear Plate. |  |  |  | 03.B).-
21 | A.- Pull backward from the "DISTRIBUTION PLATE ST1228235" until its final position. B.- Put each cable in the correct slot in the "DISTRIBUTION PLATE ST1228235". A hole will have been opened with the "ASSEMBLY FRONT PART CRYOGENIC BOX. ST1228227", when it was dragged by the movement of the "DISTRIBUTION PLATE ST1228235". TOOLINGS 2, 3 & 4 were also dargged by the displacement of the "distribution plate". |  |  |  | 03.B).-
22 | Fix the cable ties on the "DISTRIBUTION PLATE ST1228235". |  |  |  | 03.C).-
23 | A.- Move the"ASSEMBLY FRONT PART CRYOGENIC BOX. ST1228227" subassembly backwards to its final position while the cables go in the holes through the CB1 Sleeve-1's and CB2 accses. B.- Screw the 4 "SHAFT BOX-1 LHCDFHX_0055" back onto the "PLATE_FRONT PART LHCDFHX_0046". Fix it to the "Distribution plate". |  |  |  | 03.C).-
1ST CHAMBER INSTALLATION
24 | Install "TOOLING 30" to support the cables and avoid an excesive flexion on it |  | TOOLING 30 - ON SUPPORTING TRAYS OR SUSPENSION SYSTEM TO KEEP THE CABLE STRAIGHT. |  | 04.A).-
25 | A.- Weld the instrument lines "IFS WARM EXIT LHCDFHX_0018" (x2). B.- WELDING TEST. C.- Pass-through the instrumentation cables. D.- Check the electrical conections. |  |  |  | 04.A).-
26 | A.- Connect "TOOLING 4". B.- Insert the "Fillers CB1": - Central filler (TO BE DESIGN) + - "UPPER FILL LHCDFHX_0095" + - "BOTTOM FILL LHCDFHX_0096". C.- Fix with two belts until closing the CB1. | CENTRAL FILLER, TO BE DESING. LOWER FILLER NEED TO BE REDESIGNED TO ALLOW THE ASSEMBLY FROM BOTTOM. | TOOLING 4 - ON |  | 04.B).-
27 | A.- Place the two "Support cradle assy ST1348198_01" on the "Main Frame". B.- Insert the "SC LINK - DOUBLE FLANGE LHCDFHX_0005" from left to right into the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042". C.- If not installed, assemble the MLI on the left side of the LHCDFHX_0042. D.- Place the subassembly on the two "Support cradle assy". |  | Support cradle assy - ON (x2) (TOTAL INSTALLED: x3) |  | 04.C).-
28 | A.- Install the "TOOLING 3" to support the He Vessel when disconecting the "TOOLING 4". B.- Remove the "TOOLING 4". C.- Move the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042" backwards to allow reconnect the "TOOLING 4". D.- Connect "TOOLIN 4". E.- Remove "TOOLING 3". F.- Push backuntil its final position the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042" with the "MLI" and the "SC LINK - DOUBLE FLANGE LHCDFHX_0005". |  | TOOLING 3 - ON TOOLING 4 - ON / OFF TOOLING 3 - OFF |  | 04.D).-
29 | A.- Make some WELDING POINTS between the "FRONT PART CRYOGENIC BOX LHCDFHX_0047" and the "TUBE DE Ø606/3mm V5 ST1200106" (He Chamber Tube). B.- Remove "TOOLING 1". C.- Finish the WELDING from "A.-" D.- WELDING the "TUBE DE Ø606/3mm V5 ST1200106" (He Chamber Tube) to the "ASSEMBLY REAR PART CRYOGENIC BOX. ST1228237". |  | TOOLING 1 - OFF |  | 04.D).-
30 | WELDING TEST. |  |  |  | 04.D).-
CRYOBOX 1 - SC-LINC CONNECTION CLOUSURE; 2nd's SLEEVES INSTALLATION; 14/18kA CABLE PREPARATION
31 | A.- Install MLI over the welding. B.- Close the gap between "CONNECTION FLANGE TO LINK LHCDFHX_0021" (attached to the "FRAM LHCDFHX_0038") and "VACUUM CHAMBER_1 ASSEMBLY LHCDFHX_0040". C.- Install the equipment and "Closing Flanges" corresponding to "CONNECTION FLANGE TO LINK LHCDFHX_0021". D.- Remove the "Support cradle assy ST1348198_01" that supported "CONNECTION FLANGE TO LINK LHCDFHX_0021". | Sub-step "C.-" can be done after closing the machine ("STEP 74"). | Support cradle assy - OFF (x1) (TOTAL INSTALLED: x2) |  | 05.A).- 05.B).- 05.C).-
32 | A.- Install "TOOLING 6" ("SHAFT Ø25 LHCDFHX_0116" (x2)). B.- Install the "SLEEVE SUPPORT PLATE LHCDFHX_0054" (x2) on the unequipped "CB1 Support Shaft" (LHCDFHX_0118 + LHCDFHX_0093). |  | TOOLING 6 - ON SLEEVE SUPPORT PLATE GUIDING BARS (x2) |  | 05.D).-
33 | A.- Install the 2nd sleeves ("TUBE Ø84 ep 2 ST1228257" + "COLLAR ST1228242"). B.- Prepare the cables for the Splice Braidings. C.- Clamp one of the 2nd sleeves with the SLEEVE SUPPORT´s clamping systems ("HALF COLLAR LHCDFHX_0071" + "CLAMP LHCDFHX_0077"). Using the threaded rods, adjust corrctly the position of the 2nd Sleeve. D.- WELD the 2nd sleeve to the 1st one. E.- Remove the clamp and the half rings. F.- Repeat with each cable splicebox. |  |  |  | 05.E).- 05.F).-
34 | WELDING TEST of the second sleeves. |  |  |  | 05.F).-
35 | Install 3rd sleeves of CB1 (SLEEVEØ10 13 kA LHCDFHX_0075). |  |  |  | 05.G).-
36 | Cut the 14/18kA and 7kA cables. |  |  |  | 05.G).-
VACUUM CHAMBERS INSERTION
37 | A.- Install "TOOLING 3" B.- Insert "ENVELOPE CRYOGENIC BOX 2 LHCDFHX_0049" and move it as far back as possible (375mm). The cables must be passed through. C.- Disconnect temporally the "TOOLING 4" and move it forward to allow insert the "Vacuum Chambers". D.- On the "Main Frame", before "TOOLING 4", prepare the two "Support cradle assy - for bellows ST1348198_02"; and just before the "TOOLING 4", the "INTERMEDIATE SECTION SUPPORTS" (V and H guiding parts). E.- Before the bridge, assemble the "EXPANSION JOINT LHCDFHX_0003" and the "ASSEMBLY VACUUM CHAMBER TO SLEEVE ST1228841" on these sliding supports. F.- Join both sections with the “Double Claw Clamp DN630 ISO-K” (x16). G.- On the "Main Frame", between this Subassembly and the Brigde, prepare two "CENTRAL SECTION SUPPORTS" (V and H guiding parts (x2)). H.- On these, install the "VACUUM CHAMBER CENTRAL LHCDFHX_0024". |  | TOOLING 3 - ON TOOLING 4 - OFF Support cradle assy-for bellows -ON (x2) (TOTAL INSTALLED: x2) |  | 20.A).- 20.B).-
38 | A.- Move these vacuum chambers leaving a small gap wiith the "TOOLING 3", but in contact between them. B.- Connect the "TOOLING 4". C.- Disconect "TOOLING 3". D.- Assembly the "ASSEMBLY VACUUM CHAMBER TO SLEEVE ST1228841 + EXPANSION JOINT LHCDFHX_0003" with the "SC LINK - DOUBLE FLANGE LHCDFHX_0005", and this last one to the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042", using the "ISO K CLAMPS (x16)" and the "SCREW+WASHER M8 (x16)". E.- Check the alignement in this new subassy. F.- Adjust the alignement of the "VACUUM CHAMBER CENTRAL_LHCDFHX_0024" with the previous vacuum chambers. G.- Fix the "VACUUM CHAMBER CENTRAL_LHCDFHX_0024" to the "Main Frame" with the stoppers, and remove the slidding system. |  | TOOLING 4 - ON TOOLING 3 - OFF |  | 20.C).- 20.D).-
39 | A.- Remove the "SCREW+WASHER M8 (x16)" from the "SC LINK - DOUBLE FLANGE LHCDFHX_0005". B.- Remove the "Support cradle assy" (x2) from bellow "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042". C.- Move backwards the subassembly formed by the "EXPANSION JOINT LHCDFHX_0003" and the "ASSEMBLY VACUUM CHAMBER TO SLEEVE ST1228841" 960mm. D.- Move backwards the "ENVELOPE CRYOGENIC BOX 2 LHCDFHX_0049", until the "Rear plate CB1". |  | Support cradle assy - OFF (x2) (TOTAL INSTALLED: x0) |  | 20.E).-
CRYOBOX 2 + CRYOSTATS SUPPORTS +2kA CABLE PREPARATION
40 | From the two packaged cables with 6 independent cables that enter the CB2 for the 2kA current leads, form three packaged cables of 4 cables each, and cut them to their final length leaving a good excess. |  |  |  | 21.A).-
41 | A.- Install and adjust the "ASSEMBLY REAR PART CRYOGENIC BOX 2 ST1228273", without the 3rd sleeves "SLEEVEØ103 int 2 kA LHCDFHX_0092" and without the SLEEVE SUPPORT´s clamping systems ("HALF COLLAR LHCDFHX_0071" + "CLAMP LHCDFHX_0077"; "HALF COLLAR Ø107.2 LHCDFHX_0072" + "CLAMP LHCDFHX_0077"), while passing the 2kA cables through the holes in the "rear distribution plate" and the sleeves. Connect the 3 bars to the "Front Plate CB2". B.- Install the "TOOLING 10". C.- Install the "TOOLING 11". |  | TOOLING 10 - ON CB2 REAR PLATE SUPPORT TOOLING 11 - ON CONNECTION SUPPORT BETWEEN CB1'S AXE AND CB2'S AXE. |  | 21.A).-
42 | A.- Install the CB2 Fillers. B.- Close the CB2 by placing the "Envelope" in its final position, Checking the correct angular position of the He Gas Retourn connection. The envelope must be lined up with the two plates (front and rear) on its outer edge for ease the welding. C.- Install "TOOLING 3". D.- WELD the envelope to the Front and Rear Plates. If needed, remove temporaly the CB2 second sleeves "1/4 SLEEVE BOX-2 LHCDFHX_0060" and the "SPLIT RING (SLEEVE] LHCDFHX_0063". In that case, reinstall them when finish the weldings. |  | TOOLING 3 - ON |  | 21.B).-
43 | WELDING TEST |  |  |  | 21.B).-
44 | A.- Ensure that the "1/4 SLEEVE BOX-2 LHCDFHX_0060" are in contact with the "SPLIT RING (SLEEVE] LHCDFHX_0063", to have the biggest access posible to the 2kA cables. B.- Prepare the 2kA cables for the splices braiding. C.- Move forward (216mm )one of the CB2 second sleeves "1/4 SLEEVE BOX-2 LHCDFHX_0060", Clamp it with the SLEEVE SUPPORT´s clamping systems ("HALF COLLAR LHCDFHX_0071" + "CLAMP LHCDFHX_0077"). D.- Using the threaded rods system between the "REAR PART CRYOGENIC BOX 2 LHCDFHX_0059" and the "SLEEVE SUPPORT Ø84", adjust properly the position. E.- WELD the 2nd CB2 Sleeve to the 1st CB2 Sleeve. F.- Untight the Clamp System from the CB2 SLEEVE SUPPORT. G.- Repeat with the other 2 lines. H.- Tight the Clamps |  |  |  | 21.C).-
45 | WELDING TEST |  |  |  | 21.C).-
46 | A.- Unistall the SLEEVE SUPPORT´s clamping systems ("HALF COLLAR LHCDFHX_0071" + "CLAMP LHCDFHX_0077"). B.- Insertl the 3rd SLEEVEs until touch the CB2 Rear Plate (213mm backward to its final possition). |  |  |  | 21.D).-
CENTRAL VACUUM CHAMBER INSTALLATION
47 | A.- Unistall temporally the "STOPPED SHAFT LHCDFHX_0111", the "CLAMP COLLAR Ø45 LHCDFHX_0086", the "SLEEVE SUPPORT Ø84" assy, and the "SLEEVE SUPPORT Ø104". B.- On the "Main Frame", install the "VACUUM CHAMBER CENTRAL LHCDFHX_0024" with its supports and sliding systems, on the right side and after the "TOOLING 4". |  |  |  | 22.A).-
48 | A.- Install the "SUPPORT FRAME LHCDFHX_0061" and the "SHAFT SUPPORT BOX 2 LHCDFHX_0058" in the "VACUUM CHAMBER CENTRAL LHCDFHX_0024". DO NOT TIGHT THE FIXATIONS TO ALLOW THE CORRECT ALIGMENT IN FURHTER STEEPS. B.- Disconnect the "TOOLING 4". C.- Move backwards the "VACUUM CHAMBER CENTRAL LHCDFHX_0024" with the Cryoboxes axis until we have gor space enough to reconnect the "TOOLING 4". |  | TOOLING 4 - OFF |  | 22.B).-
49 | A.- Reconnect the "TOOLING 4". B.- Uninstall "TOOLING 10". C.- Move backwards the "VACUUM CHAMBER CENTRAL LHCDFHX_0024" with the Cryobox axis to its final position, taking care of the correct insertion of the "SHAFT SUPPORT BOX 2 LHCDFHX_0058" in the axis "BOX-2 SUPPORT LHCDFHX_0108". THIS SUPPORT REMAINS "FREE" UNTIL THE FINE ALIGNEMENT COULD BE PERFORMED in nexts steeps (no circlips or Pins still installed). D.- Remove the sliding system from the Central Vacuum Chamber. E.- Install the stoppers. |  | TOOLING 4 - ON TOOLING 10 - OFF |  | 22.C).-
50 | A.- Remove the "TOOLING 3". B.- Close the gap before the central vacuum chamber by displacing forward the Flexible with Intermediate Chamber . C.- Align all the vacuum chambers and the CB2 Axis Support. Tight its fixations. D.- Install the circlips and pins in between the "SHAFT SUPPORT BOX 2 LHCDFHX_0058" in the axis "BOX-2 SUPPORT LHCDFHX_0108". E.- Install the "STOPPED SHAFT LHCDFHX_0111". F.- Install the "SLEEVE SUPPORT Ø84" assy, the "SLEEVE SUPPORT Ø104", and the "CLAMP COLLAR Ø45 LHCDFHX_0086". |  | TOOLING 3 - OFF |  | 22.D).-
51 | A.- Open again the gap we closed in the previous steep. B.- Install "TOOLING 3". C.- Remove the "TOOLING 4" definitely. D.- Remove the "TOOLING 11". E.- Disconnect the "MALE SHAFT MACHINED-EXTRA LENGTH ST1367281" and connect the extension to the CB1 support shaft: "MALE SHAFT MACHINED LHCDFHX_0119" + "THREADED ROD M8- 50 mm ST1360634". |  | TOOLING 3 - ON TOOLING 4 - OFF TOOLING 11 - OFF |  | 22.E).-
52 | A.- Insert in the "MALE SHAFT MACHINED LHCDFHX_0119" the "TAILSTOCK LHCDFHX_0062". B.- Connect the "SUPPORT FRAME LHCDFHX_0061" with the "MALE SHAFT MACHINED LHCDFHX_0119" by bolting the "TAILSTOCK LHCDFHX_0062" to it. C.- Once the final position of the "SUPPORT FRAME LHCDFHX_0061" is fixed by the "TAILSTOCK LHCDFHX_0062", tight the fixations to the "VACUUM CHAMBER CENTRAL LHCDFHX_0024". |  |  |  | 22.F).-
53 | A.- Remove the "TOOLING 3" definitely. B.- WELD the "IFS WARM EXIT LHCDFHX_0018" (x2) to the "VACUUM CHAMBER CENTRAL LHCDFHX_0024". C.- WELDING TEST of each line separatelly. D.- Connect electrically and Test the "IFS WARM EXIT LHCDFHX_0018" with the "IFS DFHX EXIT LHCDFHX_0009". |  | TOOLING 3 - OFF |  | 22.F).-
54 | A.- Install the "CRYOGENIC SAFETY LINE ASSEMBLY ST1330037" and WELD the end to its connection in the "REAR PLATE BOX 1". B.- Install and WELD the "SHUTTER Ø63 LHCDFHX_0120". C.- WELDING TEST of each line separatelly. |  |  |  | 22.F).-
55 | A.- Install the "RETURN LINE ASSEMBLY-Ghe ST1329498" and WELD to the "ENVELOPE CRYOGENIC BOX 2 LHCDFHX_0049". B.- WELDING TEST. |  |  |  | 22.F).-
2kA CURRENT LEADS INSTALLATION
56 | A.- On the "Main Frame", place after the cable two "Support cradle assy". B.- On these supports, place the "VACUUM CHAMBER FLEXIBLE LHCDFHX_0006" without the "SC LINK - DOUBLE FLANGE LHCDFHX_0005" and without the O-Rings ("O-RING Ø6.99_Ø862+1.5 NBR ST1297405"; "O-RING 6.99-Ø906+1.5% NBR ST1308720"). |  | Support cradle assy - OFF (x2) (TOTAL INSTALLED: x4) |  | 08.A).-
57 | A.- Move the flexible backwards, to its postition (to make room for the Current Leads supports). B.- On the "Extension Main Frame" install the assembly "ASSEMBLY OF MODULE 3_ 2kA ST1228863" (with the exception of the flexible). |  |  |  | 08.B).-
58 | A.- Place on its final position the assembly "ASSEMBLY OF MODULE 3_ 2kA ST1228863". B.- Adjust the position of the "flexible" and the "ASSEMBLY OF MODULE 3_ 2kA ST1228863" respect to the "VACUUM CENTRAL CHAMBER". C.- Joint them with the clamps [(x16)x2] and Scrwes (x16). D.- remove the "Side support 2k frame assembly ST1360893". |  |  |  | 08.C).-
59 | A.- Unscrew the bolts fixing the "SC LINK - DOUBLE FLANGE" to the "SC LINK - OVERSLEEVE SPECIAL FLANGE ST1206289". B.- Move the "VACUUM CHAMBER FLEXIBLE LHCDFHX_0006" forwards, as much as it can be, including the "SC LINK - OVERSLEEVE SPECIAL FLANGE ST1206289". |  |  |  | 08.D).-
60 | A.- Install the "TOOLING 9" protective trays between the two "SLEEVE SUPPORT PLATE_2kA LHCDFHX_0064" (or supported by the "Main Frame"). B.- Maket the SPLICE BRAIDING on each cable. C.- Remove the "TOOLING 9". D.- Remove the cale supporting "TOOLING 30" from those ones, installed at the step 24 . |  | TOOLING 9 - ON/OFF PROTECTIVE TRAYS FOR THE SPLICES BRAIDING. TOOLING 30 - OFF PARTIALLY |  | 08.D).-
61 | A.- Move the CB2 3rd Sleeves 513mm forwards B.- Using the "SLEEVE SUPPORT PLATE LHCDFHX_0064" equipped with the CLAMP SYSTEMS for each type of sleeve, adjust and WELD the 2nd and 3rd sleeve to the current leads and between them. |  |  |  | 08.E).-
62 | TEST WELDING. |  |  |  | 08.E).-
14/18kA + 7kA CURRENT LEADS INSTALLATION
63 | Open a small gap between the 2kA support frame and the flexible, 150mm, to ease the installation of the 14/18kA current leads frame, on its final position |  |  |  | 40.A).-
64 | Install in its final position, the "18kA leads support frame welding ST1346262", without any current lead. |  |  |  | 40.A).-
65 | A.- Install the "TOOLING 7" protective trays between the two "SLEEVE SUPPORT PLATE LHCDFHX_0054". B.- Install the "Common leads 7kA assembly LHCDFLHD0008" +" Double flexible 7kA assy ST1331994". C.- Make the SPLICE BRAIDING . C.- Remove the "TOOLING 7". D.- Remove the cable supporting "TOOLING 30" installed at the step 24, for this line. |  | TOOLING 7 - ON / OFF CB1 SPLICES BRAIDING TRAYS TOOLING 30- OFF |  | 40.B).-
66 | A.- Move the CB1 - 3rd Sleeves 313mm forwards. B.- Using the "SLEEVE SUPPORT PLATE LHCDFHX_0064" equipped with the CLAMP SYSTEMS for each type of sleeve, adjust and WELD the 2nd and 3rd sleeve to the current leads and between them. |  |  |  | 40.C).-
67 | A).- Repeat the last two steeps, installing the 18kA Current Leads ("ASSY Dewar 18KA / 14kA LHCDFLHA0020" + "Double flexible 18kA assy ST1332335"), line by line. B).- Check the correct Vertical alignement of the "BLOCK 14/18 KA_LHCDFLHA0002" in each current lead line installed, because is the electric power connection interface to the 14/18kA (red faces). Use of a specific tooling or bubble level to be defined. |  | TOOLING 7 - ON / OFF CB1 SPLICES BRAIDING TRAYS TOOLING 30- OFF |  | 40.D).-
68 | SLEEVES WELDINGS TESTS. |  |  |  | 40.D).-
69 | A.- Remove "TOOLING 6" (Steep 32). B.- Remove "TOOLIG 20" (Steep 11). |  | TOOLING 6 - OFF TOOLING 20 - OFF |  | 40.E).-
70 | Install: - "LINE BREAKING DISK ASSEMBLY LHCDFHX_0100" + "DN100 - ISO K - CROSS ST0898049" + "BLANK FLANGE DN100 - ISO-K (AISI 304) ST0432309" + "VPGFY001-Assembly DFHX ST0859898" + Hardware. |  |  |  | 40.E).-
71 | Install "VPGFY003-Assembly ST0860014" |  |  |  | 40.E).-
72 | From the CB2-First Sleeve Support, remove ONLY the "HALF COLLAR LHCDFHX_0071 (x6)". |  |  |  | 40.F).-
MLI INSTALLATION + CHECKING SYSTEMS + CLOUSURE
73 | Install the MLI covering the CB1 and CB2, as well as the safety and return lines of Helium. |  |  |  | 10.A).-
74 | A.- Close the 1st bellow gap, by moving the first "EXPANSION JOINT LHCDFHX_0003" together with the "VACUUM CHAMBER TO SLEEVE LHCDFHX_0008" and the "SC LINK - DOUBLE FLANGE LHCDFHX_0005". B.- Screw the "SC LINK - DOUBLE FLANGE LHCDFHX_0005" to the "VACUUM CHAMBER FOR THERMAL DISSIPATION LHCDFHX_0042". C.- On the other side of the Bellow, connect it to the "VACUUM CHAMBER CENTRAL LHCDFHX_0024" using the "Double Claw Clamp DN630 ISO-K (x16)". |  |  |  | 10.B).-
75 | A.- Fix the "VACUUM CHAMBER CENTRAL_LHCDFHX_0024" to the "Main Frame" with the stoppers, and remove the slidding system. B.- Remove the two "Support cradle assy - for bellows ST1348198_02". C.- Remove the "Bellow's Stiffener Rods". D.- Install the "VPGFY003-Assembly ST0860014" in the SC-Link side. |  | Support cradle assy-for bellows -OFF (x2) (TOTAL INSTALLED: x2) |  | 10.B).-
76 | A.- Close the 2nd gap by moving the first "EXPANSION JOINT LHCDFHX_0003" together with the "SC LINK - DOUBLE FLANGE LHCDFHX_0005". B.- Screw the "SC LINK - DOUBLE FLANGE LHCDFHX_0005" on the "ASSEMBLY OF MODULE 3_ 2kA ST1228863". C.- On the other side of the secod Bellow, connect it to the "VACUUM CHAMBER CENTRAL LHCDFHX_0024" by using the "Double Claw Clamp DN630 ISO-K (x16)". |  |  |  | 10.C).-
77 | A.- Remove the two "Support cradle assy - for bellows ST1348198_02". B.- Remove the "Bellow's Stiffener Rods". |  | Support cradle assy-for bellows -OFF (x2) (TOTAL INSTALLED: x0) |  | 10.C).-
78 | Disconnect the "Extension-Main Frame" |  |  |  | 10.C).-
79 | Install the Current Leads Instrumentation and He Return Lines + Connection Space: "Assembly of helium gas return and instrumentation ST1335713". |  |  |  | 10.D).-
FINAL SYSTEMS CHECKING
80 | Complete Electrical and Helium system test. |  |  |  | 11).-
81 | Complete vacuum test. |  |  |  | 11).-
82 | Final test of all systems. |  |  |  | 11).-